calvary

church

Global

Outreach

#### teams

TEAM LEADER MANUAL

How can they hear, unless someone tells them…

Romans 10:14

Will YOU join the adventure to make disciples as you go into a world that so desperately needs to hear the good news of the Gospel?

Updated 2005

Compiled by: Pastor Bruce Huseby Edited by: Corey Venti

Credits:  Our Global Outreach Team Leaders,

CultureLink, SEND Int’l, International Needs Network, Peacemaker Ministries

Used with permission.

GLOBAL OUTREACH TEAM LEADERS TRAINING MANUAL

Contents

Vision and Values Statement						page 4

Policies and Procedures							page 5

Team Leaders Section – Key Steps

Section 1 - Getting Started

- Step One –Trip Approval						page 7

- Step Two –Requirements of Team Leader				page 7

- Step Three -Communication/Budget Approval			page 9

- Step Four – Advertising and Recruiting				page 9

- Step Five – Informational Meeting					page 9

- Checklist for Section One						page 9

Section Two - The Team

- Step One - Team building process					page 11

- Step Two - Choosing your leaders					page 11

Logistics Leader, Spiritual Life Leader, other team assistants

- Step Three –Finances							page 15

- Checklist for Section Two						page 16

Section Three – Planning Team Meetings

- Meeting One								page 17

- Checklist for Section Three						page 16

- Team Covenant								page 17

- Meeting Two								page 20

- Meeting Three								page 21

- Meeting Four								page 22

- Meeting Five								page 23

- Pre-departure meeting							page 24

- On-sight meetings							page 24

- Debrief									page 24

- Tools for developing a team unity 					page 25

Section Four - After the Trip

- Follow-up Meetings							page 43

- Reporting to the Church						page 43

- Section Five - Miscellaneous Information

- Global Mobilization Team Contact Information			page

- List of Travel Agencies							page

- Suggestions for Working with On-site Missionaries			page

- Translator Skit								page

- Table of Contents continued on the next page!

Table of Contents Continued

- Section 6 - Forms								page 45

- (Please use these forms as your originals and make copies of them as needed)

- GO Team Proposal							page 47

Team Leader Agreement Form						page 54

- Budgeting Form								page 55

- Project Form								page 56

- Advertisement Form							page 57

- Phone Recommendation Form					page 58

- Team Member Interview Form						page 59

- Calvary Church Statement of Doctrine				page 60

- Team Assignments Form						page 62

- Cash Advance Reconciliation						page 63

- GO team meeting dates						page 64

- GO Team member profile						page 65

- GO Application								page 71

- Participant Profile Form							page 74

Team Members Manual

Dear Trainee,

Welcome to the exciting adventure of short term missions.  You are receiving this training because you have been identified as a person who is willing to mobilize others and lead them to become more involved with the world for the cause of Christ.

We have designed this training to give you guidelines concerning how to lead an effective short-term experience.  (Global Outreach Team)  Through this material you will find clear directives.  Those directives help with everything from being a good team, to laws on finance, to health insurance.  We ask you to clearly abide by and submit to these directives.

We believe anyone who aspires to be a team leader should look first at his or her own life.  A Biblical leader is first and foremost a servant.  In reality we should be servants leading servants.  All too often the term leader gives an immature person entitlement, assumed authority, a sense of power, prestige and unique rights.  Biblically, that is not what a leader is.  They are people who are proven to be faithful, above reproach, understand authority, teachable and accountable.  Position is not something to ask for but is recognized by others as a unique gift God has bestowed.  For further study I’d encourage you to meditate on:  Matt. 20:20-28, 1 Timothy 3, Titus 1, and

1 Peter 5.

The purpose throughout all Calvary Church teams should reflect the Church’s strategy of making disciples.  That is:

  - Building Life Changing Relationships – It is our desire that any Global Outreach Team have the focus of cultivating relationships and sharing the gospel of Jesus Christ.

  - Community of Believers – It is our desire that every Global Outreach Team seek to involve nationals in a church that clearly proclaims Christ alone, the Bible as truth, and obedience in lifestyle to God’s Word.

  - Equipping the Saints – It is our desire that we equip not only people from our Global Outreach Teams, but nationals as well, to relate to, learn about, and serve others in Christ.

This material is not perfect because it was compiled by imperfect people.  So, it is a work in progress.  This most recent revision adds key components to benefit all who lead a short term missions team from Calvary Church.

I am personally looking forward to seeing how God will work in each of our lives and the lives of those we serve in short term missions to expand Christ’s kingdom.

Rejoicing,

Bruce Huseby

Missions Pastor

# Calvary Church Global & Community Ministries

# Our Mission:  MAKE DISCIPLES

## Therefore, go and make disciples of all nations, baptizing them in the name of the Father, and of Son, and of Holy Spirit, and teaching them to obey everything I have commanded you…Matthew 28:19,20

## OUR VISION:  To see disciples of Jesus Christ raised up among the least reached, least evangelized, poor and oppressed people of our world through partnerships focused on establishing and nurturing the local church.

# We affirm that:

## Jesus Christ is the only way, truth, and life…  John 14:6

## The life of faith in Christ is transformational.  2 Corinthians 5:17

## Making disciples implies spiritual multiplication.  2 Timothy 2:2

## We value:

# PRAYER

## For the transformation of the world through Jesus Christ and the work of individuals who faithfully serve to see it accomplished.  Phil. 4:6

- For laborers to enter the harvest.  Matthew 9:37,38

## Not as part of our work, but as our work.  James 5:16

# PEOPLE

## Focusing on the least evangelized, and unreached people of the world.  Mark 16:15

## Committing to the poor, oppressed, and the “least of these”  Luke 4:18,19; Matt. 24:40

## Developing strong, long term relationships with our partners.

## Effectively educating and mobilizing all age groups within Calvary Church.     Romans 10:14

- Sending workers into the harvest field from Calvary Church  - Romans 10:15

# PARTNERSHIP

## Aligning our missions efforts to focus on establishing and/or developing the local church.  Acts 2:46-47, Acts 14:27-28

## Committing to the local church and their outreach to communities.  Acts 13:1-4

## Establishing strategic partnerships among people groups and/or geographic areas with:

### National churches and leadership

### Partner oriented organizations

This section is excerpted from the Calvary Church Missions Policy and Procedure Manual

- POLICY AND SUPPORT FOR SHORT TERM MISSIONS AND SERVICE

- Calvary Church sponsored Short-Term Mission (STM) Trips

- Recognizing that STM trips are one of the best tools for putting God’s work in the world on people’s hearts, we encourage groups and individuals to participate in STM Trips.

- STM trips must have Mission Committee and Deacon approval for financial package prior to advertisement, recruitment and fund raising.  A proposal in writing must be submitted to the Missions Committee.

- “All persons approved for financial support by the appropriate committee, including short-term missionaries, will be required to sign a statement indicating that they accept in its entirety the statement of doctrine in this constitution.”  (Article VI, Section C of the Church Constitution)

- STM team leaders shall be members of Calvary Church in good standing and provide spiritual, logistical, and financial leadership.  The Mission Committee approves team leaders.

- STM trip sites should support the overall mission strategy with the priority of ministering in unreached and least evangelized areas.  When possible, those trips should support the work of Calvary Church missionaries.

- Team Selection

- Team members should be growing Christians who are active at Calvary Church.  Team members from outside Calvary Church who meet the qualifications will be accepted if space is available.

- Team members must successfully complete the application and interview process.

- Team members must agree to attend all pre-field training, on the field meetings and debriefing meetings.

- Team leaders may set age or ability standards for trips in order to ensure safety and complete the ministry goals.

- Accountability

  - Training and Debriefing- required for each trip

  - Post trip evaluation and budget accounting - to be completed by the team leader and given to the Mobilization Team no later than one month from the completion of the trip.

- Finances

Funds for a STM trip may come from the following sources.

- Team members’ personal finances

- Team members’ personal fund-raising

- Approved team fund-raising projects

- Missions Committee allocations for the project

- Emergency Travel Insurance is required for anyone traveling outside of the United States or Canada.

TEAM LEADERS TRAINING

KEY STEPS

Section One – Getting Started

Step One – Trip Approval

Understand the churches values and its policy concerning short-term missions as described in section X of the mission’s policy and procedure manual. (See page 5)  It is from this policy we begin:

Does your proposed trip fall within the overall missions strategy of Calvary Church? (X1e)

1.	We are currently developing strategic alliances in four regions: Uzbekistan, the Balkans (specifically Albania and Kosovo), NE Europe, specifically Poland and Ukraine.  As a result we desire all trips to reinforce what we are seeking to do in these regions.  Each of these regions has a team that is looking at a strategic plan to see the national church nurtured or new churches planted.  Any trips to these regions must be part of that strategic plan and approved by the Mobilization Team at least five months prior to the trip.

2.	If a trip is desired to another location a team proposal (see form #1, pg. 52) must be submitted to the Global Mobilization Team and the Pastor of Missions at least seven months before the desired trip.  They will respond to the proposal within thirty (30) days.

Step Two – Requirements of Team Leadership

Team Leadership is established, by an interview, with the Global Mobilization Team (contact info p. 46) and should be completed during the initial process.  A signed agreement (see form #2, p. 59) by the team leader and chair of the Global Mobilization Team is required to continue the process of leading a GO Team.

  - Prayerfully consider and make sure this is what God desires of you.

  - The leader of a GO Team is the individual most responsible for the team, its activity, and ultimate effectiveness.  Team leaders are responsible for designating tasks, group preparation, and final debriefing.  The most important aspect a team leader needs to understand is their role of disciple-maker.  The relational ministry a leader has with each team member should go beyond the preparation, trip, and debrief.  It is long-term life on life.  1 Thess. 2:8.

  - The Team Leader is responsible for every aspect of the short-term mission trip, either directly or through the delegation of specific tasks.  These include:

        - Establishing and maintaining a direct line of communication with the Global Mobilization Team (contact info p. 46).

        - Pre-trip contact with missionaries and/or other hosts.

        - The preparation and coordination of trip publicity with the Missions Secretary.

        - Overseeing application and team selection process.  This means calling references, setting up interviews, and attending the interviews of potential team members.

        - Team preparation and meetings, making sure participants attend every meeting.

        - Appointment of a Logistics Leader.

        - Appointment of a Spiritual Life Leader.

        - Making sure all finances are handled appropriately and properly.

        - Final debriefing after return and mission completion.

  - The Team Leader’s affect on the team is extensive.  Team Leaders ensure the fulfillment of the technical aspects and, even further, set the mood for the team.  They serve as mentor, motivator, encourager, and example to the team.  Every team leader should block off individual time with each team member during the GO Trip.  For these reasons, it is crucial that any individual considering this position do so with much prayer and careful deliberation.  Likewise, the Global Mobilization Team will give prayer and consideration for its recommendation for approval to the Missions Committee of every Team Leader.

  - Attend the mandatory team leader training.

This is a requirement because of consistent refining, lessons learned, and our commitment to discipleship.

Step Three - Communication/Budget Approval

1.	Is the Pastor of Missions Administrative Assistant (AA) aware of your trip?

Don’t assume since you have communicated with the Pastor of Missions that his AA knows about the trip.  Your relationship will be of utmost importance, as you will see later in this document.  All advertisement for a short-term trip must be cleared through the missions AA.

- Have you established your planned budget? (see form #3, p. 60)

- Have you obtained Missions Committee and Deacon approval for your trip? (X1b)  This is essential if you desire Calvary Church to accept donations for your short-term trip.  It is also essential for advertisement in any church publication. No unapproved trip may advertise in any Calvary publication and its promotion is not allowed within the church structure.

  - The Project Form (form #4, p. 61) should be submitted following approval of the team proposal to the Missions Office.  This process by the Missions Committee and Deacons usually takes 45-60 days so plan well in advance.

  - This Project Form should include your purpose, anticipated budget, location, dates, and a starting and ending point for donation to be received.   This should be turned in yearly even on recurring trips so that the board can have the financial picture.

Step Four - Advertising and Recruiting

Start Advertising, recruiting, and plan when you will have an informational meeting for those with interest in the trip. (See Form #5, p. 62)

Step Five-Informational Meeting – 1 hour

## At least 4½ months prior to your trip an informational meeting should be held (see checklist for step one).  The Meeting should consist of:

### The trip objective

### The strategic plan

### Proposed Budget

### Passing out application packets (including doctrinal statements) (Form 8 pgs. 65-66 and applications (pg 70-73).

### All meeting dates (Form 11 p.69)

Checklist for Section One:

- Approval of trip. (should be done at least seven months in advance of trip).  Form # 1, p. 57

- Approval of team leader (seven months prior to departure)

Date of interview with Global Mobilization Team:

- Sign Team Leader Agreement.  Form # 2, p. 59. Date

- Submission of Budget.  Form # 3, p. 60 Date:

Date submitted to Missions AA:

- Approval of Missions Committee/Deacons – Form #4, p. 61

Date submitted for approval:

- Inform Administrative Assistant 956-9377 x206

Date of Contact:

- Attend Team leader Training.

- Begin Advertising and Recruiting for trip.  Form # 5, p. 62.

- Set Informational Meeting date.  Date:

Informational Meeting

- Have copies of objective

- Have copies of strategic plan

- Have copies of proposed budget

- Application Packets

- Schedule of Meeting Dates

- Schedule of Interview Dates

- Reference forms

###### Section Two – The Team

Team Selection –

It is the unwavering belief of Calvary Church that any short-term mission team from Calvary, regardless of whether or not it is funded by the church, represents Calvary Church to the world.  Therefore, it is crucial that each member of a GO (Global Outreach) team be a growing Christian and represent the same beliefs and ideals of the church. (See Statement of Doctrine on pages 65 & 66) While priority of support will be given to church attendees, any individual who passes the application process need not be a Calvary Church attendee to participate in a Calvary Church GO trip.

Each individual who wishes to participate in a GO Trip should first pray and seek God’s clear leading for this trip.  They then must fill out the GO application in its entirety.  A team member selection committee will be appointed from the Global Mobilization Team.  Among the members of this selection committee will be the Team Leader.  Interviews for every applicant will be held by this group.  As some mission efforts have special demands, the selection group may set limits based on age or ability for trips in order to ensure safety and completion of the ministry goals.

Step One - Know your team building process

## 1	The Application

### -Every Member of your team must fill out an Global Outreach Team application (see pages 70-73)

## 2.	References

### -Three references must be submitted per applicant with at least one reference from a pastor/ministry leader. (see form # 6, page 63). YOU are responsible to reference applicants

## 3.	Interviews

### -Each applicant must go through an interview process.  As the team leader you should schedule these interviews with yourself and at least one member of the Global Mobilization team and/or a Missions Committee Member. (see form # 7, page 64 for interview form.)

## 4.	The Doctrinal Statement (X1c)(from article VI Section C of the Calvary Church constitution) (see form # 8,  pages 65 and 66)

5.	Name Clearing – A list of your proposed team should be turned in to the missions AA following your informational meeting to be reviewed by other team leaders for insights and advice

# Step Two – Choosing Your Leaders

## 1.	The Logistics leader

In mission teams of four or more individuals it is required of the Team Leader to appoint a Logistics Leader to handle the many technical and micro details of the mission.  Selection of the Logistics Leader is at the discretion of the Team Leader.   Responsibilities would include:

A.	Financial transactions of the team.  You will need to contact the Missions Administrative Assistant to schedule a meeting with her and the Finance office to go over the financial issues.

Information to turn into Missions Administrative Assistant

i.	Turn in a team list with names, addresses, phone numbers, and email where applicable.  On this list please indicate team leader, logistic leader, and spiritual life leader. (Form 13)

ii.	Flight information

iii.	Emergency Contact information while overseas if available.

* A comprehensive form for the entire team is Form 14, page 74.

B.	Working with travel providers to obtain the best cost for transportation. (See page 47)

C.	Making sure every team member has received proper medical, preparation, passports, visas, and any other required documentation to be in any country in which the team will enter.  Before the trip make sure you have the following documents for each team member with you:  Permission Forms, Copies of Passports, Copies of Birth Certificates, Travel Insurance Information, and Drivers License.  The full legal name needs to be consistent in all documents.

i.	Visas:  Does the country you are going to/through require a visa?

a.	If you are not sure, check it out at www.passportsandvisas.com.

b.	If a visa is required seek assistance in obtaining it from the on site missionary you are working with.  Ask them for help in filling out the application.  The worker will also help with wording for secure countries.

c.	To retrieve the visa application and instructions do an internet search for the Embassy of the country you are traveling to/through.  Print out the application and instructions for a visa.

*  Remember if funds are needed 2 weeks is required for a check request.

D.	Obtain emergency medical insurance for the team. (required)  The Missions office will provide suggested companies for this insurance.

E.	Work with the team leader in setting up the geographical, language, and cultural distinctive for the team.

## 2.  The Spiritual Life Leader

Within every team the spiritual life of the team is essential.  The Holy Spirit is the initiator and sustainer of unity.  As a result, our dependence on Him must be every GO team member’s desire.  The Spiritual Life Leader is an optional leadership position, but is highly encouraged for teams of more than ten individuals.

The Spiritual Life Leader is responsible for:

A. Developing a prayer team and encouraging team members to develop at least 4 prayer warriors for their trip

B. Leading spiritual development times at team meetings

Examples of books for personal study and discussion at team meetings:

- The Life You’ve Always Wanted - John Ortberg

- Descending Into Greatness - Bill Hybels

- Improving Your Serve - Chuck Swindoll

- Cost of Discipleship – Dietrich Bonnhoeffer

- A Mind for Missions – Paul Borthwick

- Character - Bill Hybels

- Called and Accountable – Henry Backaby

Key issues to deal with in preparation should include:  The sovereignty of God, spiritual warfare, purity, integrity, servant hood and having a ministry mindset.

C.  Oversee spiritual formation during the trip through devotions, prayer, and other areas such as:  solitude, prayer walks, prayer partners, fasting.  The spiritual leader needs to be sensitive to issues that surface during a trip such as: discouragement, grumbling, complaining, pride, lack of submission, disunity, and lack of flexibility.

D.  Upon arrival to the country where you are ministering, it is highly recommended that the team be lead in a prayer walk around the premises or through the streets before ministry begins.

4. Apprentice Team Leader

Our desire is to reproduce leadership. If there is an individual whose gifts have demonstrated leadership ability on past GO trips, they may be recommended by the team leader to the Missions Pastor. There is a limit of one apprentice leader per trip. The goal of this process is to see the apprentice become a team leader in the future.

Other team assistants

You have many things to accomplish as a team leader and yet you do not have to do it all.  The art of delegation is a wonderful art for leadership.  We highly suggest you delegate certain things to your team members.  They can assist you in making the team function well together.

Here are some of those positions.  You may not need all of them in your particular ministry situation.  But you will need most of them.

- Music Coordinator.  Teams always have the opportunity to participate in the ministry of music.  They need a leader who will facilitate this ministry.

- Drama Coordinator:  Teams also have the opportunity to participate in the ministry of drama.  One person is needed to make decisions and direct.

- Team Medic.  You will be taking a medical kit with you and one person needs to be in charge of that.  This person will also distribute medicines, etc.  Possibly there is a nurse or doctor on your team.

- Media Coordinator.  This person could carry a team camera for a slide show as well as a video camera if available.  Just make sure he/she gets in some of the pictures.  Meet with Bob Vermeulen before the trip. Bob can be contacted by calling the church at (616) 956-9377.

- Luggage Coordinator.  This person usually is the one who is responsible for making sure all luggage gets from one place to another.  They count the bags and are often called upon at a moment’s notice to know the status of the luggage

- Carry-on Coordinators.  These two people are responsible to watch the entire carry-on luggage in airports, train stations, etc. while the rest of the team are moving other luggage.

- Food Coordinator.  Sometimes a team has to cook their own food.  This person would be the main person who makes menus, runs cooking staff, keeps track of stock, etc.

- Tool Coordinator.  If you are doing a construction project of any sort, there may be a need to coordinate the tool distribution daily as well as inventory.

To keep a list of these assistants please see Form 9, p. 67.

# Step Three - Finances

Team Leadership

            - Team Leader – The Team Leader will receive 100% funding for the GO trip from the Missions Budget

            - Logistics Leader – The Logistic Leader will receive 50% funding for the trip from the Missions Budget.

Office Procedures

- All monies should be sent to the church from donors to the Finance office.

- The Finance Office will set up an accounting system for each GO trip. Current reports are available every Thursday morning.

- The Logistics Leader should be in communication with the Missions Office concerning balances and deadlines.

- Please notify the Missions Administrative Assistant two (2) weeks in advance of the date funds are needed.  She needs to know the method of payment (check, credit card, cash advance) and how much is needed.

- All materials purchased before the departure of the trip must be turned in for reimbursement prior to departure.  The team leader must give approval for reimbursement.

- There is no reimbursement for foreign currency upon return from the trip.

Cash Advances and Receipting

1.	Cash advances for a trip will not exceed funds available in a trip account.

The Missions Office requires that every team set up a schedule of funds due.

2.	Expenses incurred during the trip, should be handled through the logistics leader who will reimburse for monies spent.

  - A specific accounting of each expenditure is needed. (see form 10, p. 68)

  - All receipts and accounting needs to be turned in to the Missions Office within five business days of your return from any GO trip.  This signifies closure of all of the financial transactions for the trip.

Support Raising Schedule

Each team member should know the expectations for their support raising.  Please establish this schedule to pass out to team members for the first team meeting.  Also, give a copy of this schedule to the Missions Administrative Assistant after your first meeting.

- Deposit amount (to be determined by the team leader).

- 50% of funds should be raised 60 days prior to departure.  You want to make sure that this is equal to the approximate cost of flights.  If your flights cost more than 50% of the trip cost than give an exact dollar amount for flights.

- 100% of funds should be raised 4 weeks prior to departure.  This is necessary so that the team leader/logistics leader can turn in the appropriate paperwork for cash advances.

The logistics leader will need to keep the team leader up to date if a team member does not have adequate funds for these deadlines.  The team leader will then meet with the Pastor of Missions so that the appropriate decisions can be made regarding the individual team members.

Postage for Support Letters:  Calvary Church will not pay postage for the mailing of support letters for GO Team members.  Each team member is responsible for his/her postage costs.

Checklist for Section two

- Praying for the right people to be the Logistics leader and the Spiritual Life leader (if needed)

- Begin to identify other ministry leadership roles

- Interview applicants

- Reference check applicants

- Turn in list of scheduled team meetings (Form  #11, p. 69 to missions office)

- I understand the financial structure.

Section 3 – Planning Team Meetings

Team meetings are not only essential, but also a required part of Calvary Church’s Global Mobilization process. The Goal of this section is to help you in designing your team meetings.  Once the team has been selected, the team members must meet at least five times prior to the trip.  Two of those meetings should be within thirty days of the trip.  These meetings should be well structured and led by the Team Leader.  At the meetings, members should have their questions answered and receive the necessary information for the trip in writing.  There must be at least one post-trip meeting to debrief and share.  This should occur within thirty days of return.  Team meetings are mandatory for participants of any GO team.  It is ultimately the team leader’s responsibility to make sure the meetings take place.  Pre-trip meetings are crucial to developing a level of organization, trust, teamwork, prayer and friendship among team members to share and reflect and find ways to incorporate ministry experiences into everyday life.

Meeting One – 1½-2 hours  - At least four months before departure.

This meeting sets the tone for your team and should be planned in detail with the following components.

A. Relational time – Get people to share why they want to be part of this team

  - Spiritual time – Develop a devotional dealing with becoming a world Christian

  - Logistics

      - Explain Passport/Visa Process (Details in Team Members Manual, Pg. 6).

      - Program time – List of ministry areas needed.

      - Collect deposit money

      - Prayer time

      - Support Raising Schedule

      - If necessary, Driver approval Forms (available in facilities office)

      - Liability Medical Forms (p. 48)

Team Leader checklist for after meeting one

- Identify logistics leader (see page 13)

Have them set up meeting with mission’s office

- Identify Spiritual life leader (see page 14)

- Participant list to missions office

- Collected deposit money to missions office

- If applicable make sure everyone has applied for a passport within one week of this meeting.

Additional Meetings

The additional meetings are required to make the short-term experience effective.  You many schedule as many as deemed necessary, but we recommend an additional four meetings to cover specifics.  One area that is an option, but also a strong recommendation is the development of a team covenant.  This helps deal with a multitude of issues that may arise on you GO trip.

Team meeting Two 2-2½ hours – at least 3 months before trip

  - Spiritual Preparation/Devotions				15 min

Study:

  - Relational Team Preparation 				15 min

(Ideas on pages 29-32)

  - Logistics 							15 min

(A logistics leader should have been appointed prior to this meeting.)

    - Passport check

    - Collect Money not sent into office.

    - Share Account Information

    - Share timeline of funding (funds to cover flight costs will be needed by next meeting)

    - Will need to have copies of Birth Certificates

    - Visa Information (if necessary)

  - Code of Conduct/Covenant (pg 7)				15 min

  - Your Story – Writing your testimony			30 min

(See Personal Preparation Section of the Team Members Manual)

  - Cultural Study						30 min

(See Cultural Section of the Team Members Manual)

  - Team Assignments

(see page 15 for ideas, use form 9 for the meeting)

  - Prayer Time

Team Meeting Three – 2½-3 hours at least two months before trip

* 50% of funds should be received for each participant at this point

A. Spiritual Preparation					    15 min

Study:

B. Relational/Team Prep					    60 min

DiSC – This exercise will assist in team dynamics

Use pages 33-35

C. Logistics

      - Collect passports (for copying and sending away for visas, if needed)

      - Collect Money not sent into office. (Amount due should cover flight costs if applicable)

      - Account Information

      - Collect copies of Birth Certificates

      - Review immunization if needed

      - Timeline information

## D. Share and fine tune your testimony			15 min

## E. Language Study						15 min

## F. Cultural Study						15 min

## G. Team Preparation						30 min

## H. Prayer time

Team Meeting Four – 3-4 Hours	30 Days before trip

* 100% of funds for each participant should be received at this point

Combining team meeting 4 and 5 in a retreat setting would be a wonderful way of becoming a cohesive team and allows for a deeper, less hurried pace (see example on next page)

A.	Spiritual Prep						15 min

Lesson:

B.	Relational/Team Prep					15 min

Idea:

C.	Logistics							30 min

- Flight Information

- Luggage Information

- Passports Returned/ w/Visas

- Account Information

- Collect all funds not turned into office – Final Payment due at this meeting.

- Collect copies of immunization records

- If using Calvary vehicles, all drivers should be approved by this meeting.

D.	Language/Cultural Study					45 min

  - Team Prep							60 min

  - Review Covenant(pages 26-28)/Peacemaking (pages 36-42)

30 min

  - Prayer Time

# Team Meeting Five 3 hours – 2 weeks before trip

A.	Spiritual Prep						15 min

B.	Relational/Team Prep					15 min

Idea:

C.	Logistics						20 min

- Final Details

  - Flight

  - Emergency Numbers

  - Lodging/Other

- Review Packing/Luggage Details

- Account Information

D.	Cultural/Language Study				45 min

E.	Team Prep						60 min

  - Prayer Time

Retreat Example ( Combining meetings four and five)

Friday

6 PM	 	Depart Calvary Church

7 PM		Arrive Facility/Get Settled

8 PM		Session One:  Worship, Study, and Prayer

9 PM		Relational/Team time – Games

10 PM		Snacks/Good Night

Saturday

8 AM	 	Breakfast

9 AM	Session Two – Devotionals, Prayer, and overview of spiritual climate of the trip sight.

10 AM		Team Building exercise - “ropes course” or similar

11:30 AM	Team Prep

12:30 PM	Lunch

1:00 PM	Logistics

2:00 PM	Worship – Personal Prayer Walk

3:15 PM	Debrief

4:00 PM	Depart

5:00 PM	arrive @ Calvary Church

Pre-Departure Meeting – TEAM Meeting Six

This meeting should deal with any last minute details, but its primary purpose is to fellowship with participant’s families, and to spend a good amount of time in prayer for the trip.  This is a good time to have your checked bag packed and weighed prior to the trip.

On Sight Meetings

Every team leader should have daily team meetings while on the trip.  This helps sustain unity, purpose, and focus.  Team meetings should have the following ingredients.

1.	Devotional Time

2.	Report on the good, bad, and ugly of recent work.

3.	Share plans for the upcoming day.

4.	Prayer

Debriefing Outline

Understanding the critical role that debriefing plays in the Global Outreach Team process is extremely important.  Debriefing is simply the process of making sense out of the GO experience and using it appropriately to help shape future attitudes and actions.  It is very important that each team member is helped to “process” what they have learned about who they are, and God’s work in the world.  Lack of sufficient “processing” can have a negative impact of his/her life.  But where those issues are faced and dealt with, they can be greatly used by God to facilitate significant new self-understanding and enable greatly expanded ministry.

Simply stated, what you are after is helping the SHORT TERM GO Team participant to come up with the answers to the questions:

- What am I learning about myself?

- What am I learning about God’s work in the world?

- What can I apply and use from what I’ve learned?

- What will my spiritual growth translate into changes in my lifestyle and ministry?

- What am I learning about my future?

Introduce these questions during the training and use them to structure your debrief.  Then, help each person come up with an action plan to implement the desired changes which surfaced during the evaluation and debrief process.

In setting up a three to six hour debriefing session, the following sequence has proven helpful in a number of churches.  Optimally the session includes not only trip participants but also missions committee members and other pastoral and lay church leadership (including counselors as needed).

- Have all team members fill out the debriefing evaluation (p. 43 of team member manual) within a week of return from trip.

- Introduce the session by reminding the participants that God’s primary purposed in this, as in everything, is to draw us (and others) to Himself and that includes changing us by putting us in situations far out of our “comfort zone.”

- Give each team member the opportunity to share some of the highlights of their trip.  This could include slides or video or their scrapbook page.

- Take time for each participant to reflect alone on personal issues raised during the trip by using a written set of questions.

- In small groups of 3-5 ask individuals to share their personal response to the trip using the personal reflection sheet as a guide.  Conclude the sharing time by helping them set up (a) a follow-through plan, (b) an accountability structure and (c) a time of group prayer addressing the issues raised in the sharing.

- Gather all the participants together and conclude the session in a time of worship and prayer.

If a team is struggling through this process, please seek assistance through the Missions Department.

Team Unity Tools

TEAM COVENANT

Your team should write a Team Covenant.  This is where you decide as a team the standards and conduct to which you will all adhere while serving on the field.  You will write it together and then your signature will seal the covenant with your teammates.  This will confirm that you will follow these standards.

You are representing your church, your city and your country but most of all the Lord when you visit another country as a group.  Your attitudes and behavior needs to be Christ-like and your goal in writing this Team Covenant is to set the standard for Christ-like behavior.

We suggest that you discuss each area as a team.  One or two of you will be appointed by your team leader to do the actual writing of the Team Covenant at a later time.  Please look actively for Scripture for your standards and quote them with the standard.

These are the following areas that we want you to consider:

- Overall purpose.  (Include your ministry objective).  The purpose statement is a one-two sentence summary of what the GO trip is all about and where.

- Discussion of Politics

- Discussion of Doctrine

- Team Unity

- Accountability

- Interpersonal Relationships

General

Team Members

Relationship with the Opposite Sex (both on team and with nationals)

Conflict Resolution

Exclusion

Number of People to a Group

Accountability Partner

Team Leadership

Missionaries

Nationals

- Time

- Flexibility

- Dress

General

Specific (for specific ministries)

SAMPLE TEAM COVENANT

TEAM COVENANT

OVERALL PURPOSE:

To continue building our relationship with the Body if Christ as servants to our adopted church and seminary in Odessa.

“If you have any encouragement from being united with Christ, if any comfort from His love, if any fellowship with His Spirit, if any tenderness and compassion, then make my joy complete by being like-minded, having the same love, being one in spirit and purpose.  Do nothing out of selfish ambition or vain conceit, but in humility consider others better than yourselves.  Each of you should look not only to your own interests, but also to the interests of others.  Your attitude should be the same as that of Christ Jesus...” Philippians 2:1-5.

“I long to see you so that I may impart to you some spiritual gift to make you strong - that is, that you and I may be mutually encouraged by each other’s faith.”  Romans 1:11-12.

As a member of the 2003 Ukraine Team, I purpose to adhere to the following covenant:

###### Politics

Team members will refrain from discussion of politics and will only respond in generalizations and in a positive manner.

###### Doctrine

Team members will support the Doctrinal Statement of our Church and will be prepared to share our doctrine in a loving and understanding way.

###### Credibility to the Task

Our task is to provide assistance in the construction of the church and seminary, to provide medical and dental care, to help in church outreach through evangelism, singing and puppetry, to provide teaching in youth ministry, health education and to assist in any way possible.

Unity of the Team

“Therefore, as God’s chosen people, holy and dearly loved, clothe yourselves with compassion, kindness, humility, gentleness and patience.  Bear with each other and forgive whatever grievances you may have against one another.  Forgive as the Lord forgave you.  And over all these virtues put on love, which binds them all together perfect unity.”  Colossians 3:12-14.

###### Gifts

Gift giving in the homes will be done as you feel led and with discretion.  At the church and seminary site, we may give gifts as God leads.  We will give our monetary gifts to Pastor Eugene at the church and to Sergei Sannikov at the seminary.

###### Accountability

Each team member will set aside time daily for individual, private time with the Lord.  We will continue to be accountable to our prayer partner and to each other.

###### Interpersonal Relationships

Conflict Resolution

If any problems arise between team members, we commit to praying about it first, and if necessary, speaking privately and personally to that member in a loving, Christ-like way to resolve the issue.  If it cannot be resolved between the two, then we commit to going to the team leader.

###### Relationships with Nationals

We will use good judgment regarding initiating physical contact with the nationals in public and in private.

###### Team Leadership

As an ambassador of the Lord Jesus Christ, the United States, Calvary Church and the Ukraine Team, I will strive to be above reproach in my actions and attitudes.  I will respect and submit to the authority of the team leader.

Time

We commit as team members to be as punctual as possible to all scheduled team and host events unless excused by the team leader.

Flexibility

By not merely looking out for our own interest, but also the interest of others, each team member will be flexible at all times about unexpected changes in schedule and/or events.

###### Dress

We are committed to being culturally relevant in our dress when at the church and seminary site.  Ladies will wear skirts at the work sites unless instructed otherwise by the nationals.

We so now, in the presence of God, enter in this GO team covenant, as we go forth as one Body in Christ for ministry in Odessa, Ukraine.

Signature_________________________________

Date_____________________________________

Description of Initiative Games

These are samples of initiative games.  Remember, you are free to invent your own.

Human Machinery

The group forms a large circle.  One person goes to the center of the circle and moves and makes sounds to represent a machine part.  Then a second person goes to the center of the circle and joints him/herself to the machine with a complimentary machine motion and noise until everyone in the group is involved.

Lineup

Each member is blindfolded.  The group is then instructed to line up by height, without any talking.  (Don’t tell them whether to go in ascending or descending order; that is part of their task).  This idea can be repeated with talking for such things as birth date, shoe size, etc.

Blind Rescue

Each individual is blindfolded.  The instructor then takes one member and places him/her in a spot away from the group.  The group must then organize a search to find the missing person.  The missing person may not talk or signal the others in any way.  A large open area is needed for this game.

Blob Walk

The group forms a circle facing each other.  While holding hands, the group must ascend a steep incline or traverse a heavily wooded area to an identified destination.  This is a good way to unload your car, van, or bus for a cookout.  Simply drop them off a reasonable way from the destination and have them “blob” through the woods to reach where the grills are preparing lunch.

Handicapped

The object of this exercise is to move your team from one place to another.  How you get them there is the challenge.  Everyone is given a handicap or multiple handicaps. Blind deaf, mute, lame, blind and lame, deaf and mute, and so on.  The goal is to work together as a team to get to a desired destination over, under and through obstacles.  It really takes teamwork, which is the idea.

Broken Squares

Broken Squares is in instructional game in cross-cultural communication and problem solving.  The purpose of the game is to sensitize the participants to the problems involved in cross-cultural communication and problem solving as a team.

Time Required:  45 minutes (15 for Simulation, 30 for Debriefing)

Participants:  Broken squares is played in groups of five.  If you have 12 people on your team, have two groups of five and allow the other two people to be observer/judge.  Each group of five will need their own set of Broken Squares (the pieces to the game are available for check out in the Missions Department).

Materials and Set-Up:

- One set of Broken Squares for each group of five.

- Each group of five should be seated around a table where they can see each other

- The observer/judge should be given a copy of the instructions.

Instructions:  The following instructions should be read to the entire group.

You are now going to play Broken Squares.  Some refer to it as the society of

Squaresville.  There are rules that must be observed to function in the new society.  You may not like the rules, but to make the “cultural” adjustments and to accomplish the task assigned, you must be careful to observe them.

The task before you, as a group, is to have a completed square finished in front of each person.  There is to be no talking.  You may give away the pieces of the squares in front of you.

Again, The purpose of the game is to have the same size square completed in front of each person in the group.

Again, you may give away the pieces in front of you, however you may not:

- Place your pieces in another person’s square.

- Place your pieces in the center for others to take.

- Gesture with your hands, arms, eyes, etc.  to communicate to another person to ask for a piece.

In order to accomplish the goal of the game of completing a square in front of each participant, the only thing you can do is give your pieces away.

Open your envelopes and get started.

Making Broken Squares

A set consists of five envelopes containing pieces of cardboard or paper cut in different patterns which, when properly arranged, will form five squares of equal size.  One set, of five envelopes, should be prepared for each group of five players you have.

To prepare a set, use 6”x6” squares.  Prepare five squares.  Draw lines on the squares using the patterns below as a guide.  Place the letters on each square’s sections.  The small triangles in squares 1, 4, and 5 should be the same size.  The pieces in square 2 marked with letters “B” and “E” should be the same size.

After the lines have been drawn on the squares and the letters marked.  Cut the pieces of the squares using the lines as your guide.

Take five envelopes labeled A, B, C, D, and E.  Place the pieces with the corresponding letter in each envelope.  These are the five envelopes to give the five players.  There should be the following number of pieces in each envelope: A-3, B-4, C-2, D2, E-4.

B

D

D

E

A

E

A

A

B

B

E

E

B

C

C

6”x6” squares

# Instructions for Observer/Judge

Insure participants keep the rules:

- No talking, pointing, etc.

- No taking pieces or placing of pieces into another person’s square.

- It is permissible to give away an entire square.  It is not necessary to give one piece away at a time.

Look for the following:

- Who has difficulty keeping the rules?

- When the frustration level rises and what helps to resolve it?

- Who is willing to give away pieces?  Who holds on to them?

- Who looks for solutions from other people’s pieces and who only concentrates on their own pieces?

- Who develops a means of communicating?

- Who becomes the group leader?

- Who quits?

- Who creates problems?

- Who solves problems?

# Debriefing the Game

It is important to let the team express themselves after the game.  Some members will be proud that they finished their square and quit…when the goal is to have a completed square in front of each person.

Communication

Ask the following:

- What were your feelings?

- Did you feel frustrated?  Why?

- If the frustration was caused by communication, how did you solve the problem?

- If the frustration was caused by another team member, how did you deal with this?

- What messages are sent by one’s willingness to or lack of willingness to give away pieces?

Note:  The problem in cross-cultural communication is not that you can’t communicate, but that you have been robbed of your normal way of communicating.  You were given a communication means – giving your pieces away.

Problem Solving

Ask the following:

- What difficulties did your group face?

- Who felt they were finished when they completed their square?  What does this say about looking out for only your interest?

- Did you hear the instructions individually when they were clearly stated in group terms?  If so, why?  What does this say about team dynamics?

- How could you have worked more effectively as a team?

- What principles have you learned from this exercise which can be applied in your cross-cultural experience?

Note:  Observer/Judge may want to share their observations.  Invite the Judge to share after the discussion has progressed.

Personality Profiles

"D" Behavior (Active/Task Oriented)

Abilities:  Lead, take stand, confront issue, persevere, dictate, make decisions and control.

Opportunities:  Organize needed ministry, chair Stewardship Committee, head Usher's Committee, commit to specific challenge.

Warning:  You want to control everyone, but must first control yourself.  Remember, "to have authority, you must be under authority."  Be loyal to your leaders.

Reward:  Follow your spiritual leaders.  Allow Christ to be Lord of your life, and God will use you in a great way to move the ministry forward.

Prayer:  "Dear God, control my driving, demanding and dominant personality, so I can be a strong and peace-making leader for your glory.

"I" Behavior (Active/People-oriented)

Abilities:  Communicate, inspire, influence, make friends, optimism, enthusiasm.

Opportunities:  Give testimony, drama, social committee, greeter, encourager, lead discussion group and visitation.

Warning:  You naturally outshine others.  Don't serve purely through your "personality."  Also, pride and sinful lusts will destroy your testimony.

Reward:  God designed you to shine for Him.  When you allow Him to shine through you, He will use you in greater ways than you ever imagined.

Prayer:  "Dear God, keep me humble to do your will, not mine.  Help me give you and those who praise me the credit for all You have done."

"C" Behavior (Passive/Task-oriented)

Abilities:  Analyze, improve, discern, calculate, follow directions, do the right thing.

Opportunities:  Finance Committee, long-range planning, office, record information, research, teach, organize and order curriculum.

Warning:  Due to your cautiousness, criticism comes easy.  Don't ways be pessimistic and hard to convince.  Increase your faith in God and truth those you follow.

Reward:  Ministers need competent people to fulfill their visions.  You can be a great blessing if you continually look at the possibilities, rather than the impossibilities.

Prayer:  "Dear God, help me be optimistic in the midst of problems - a source of encouragement to those who find faith and victory difficult.

"S" Behavior (Passive/People-oriented)

Abilities:  Support, serve, specialize, finish what others start, work behind the scenes, and do what needs to be done.

Opportunities:  On call whenever needed, hospital visitation, encourage new members, office, keep records, telephoning and counseling.

Warning:  Shyness hinders your opportunities to do great things for God.  Be more aggressive and assertive.  Be careful, people my take advantage of you.

Reward:  Believing God's promise that you can do all things through Him who strengthens you, step out and try the difficult.  You may be surprised what God can do.

Prayer:  "Dear God, I know you use the weak things to confound the mighty and I often don't feel capable of serving you, but through your grace I will."

How to Handle Conflicts

"D" Behavior

Under pressure:

Becomes dictatorial, domineering, demanding, angry, intense, forceful, direct, bossy.

Sources of Irritation:

Weakness, indecisiveness, laziness, lack of: discipline, plan, purpose, direction, authority, control, challenge.

Needs To:

Back off, seek peace, relax, think before reacting, control self, be: patient, loving, friendly, loyal, kind, sensitive.

"I" Behavior

Under pressure:

Becomes hyper, overly optimistic, immature, emotional, irrational, silly, wordy, selfish.

Sources of Irritation:

Disinterest, slowness, pessimism, details, time restraints, antagonism, doubt, structure, lack of: enthusiasm, team participation.

Needs To:

Listen, count the cost, control emotions, be: humble, strong, disciplined, punctual, careful with words, conscientious.

"C" Behavior

Under pressure:

Becomes moody, critical, contemplative, negative, worrisome.

Sources of Irritation:

Incompetence, disorganization, foolishness, dishonesty, inaccuracy, wastefulness, inconsistency, blind faith, false impressions.

Needs to:

Loosen up, communicate, be: joyful positive, tolerant, compromising, open trusting, enthusiastic.

"S" Behavior

Under Pressure:

Becomes subservient, insecure, fearful, weak-willed, withdrawn, sympathizer, sucker.

Sources of Irritation:

Pushiness, instability, inflexibility, anger, disloyalty, insensitivity, pride, discrimination, unfairness.

Needs To:

Be:  strong, courageous, challenging, aggressive, assertive, confrontational, enthusiastic, outgoing, expressive, cautious, bold.

Natural Responses to Conflict			Recommended Wise Responses

"D"s - Want to Attack 				"D"s - Restore with Love

"I"s - Want to Expose Others				"I"s - Make others look good

"S"s - Want to Support or Submit			"S"s - Care enough to Confront

"C"s - Want to Criticize				"C"s - Examine Own Self first

Conflict Resolution

(This material is used by permission of Peacemaker Ministries, Billings, MT)

Conflict can make life very awkward. It often catches us off guard and leads us to say and do things we later regret. When someone offends us, we often react without thinking. Soon it is as if we are sliding down a slippery slope and things are going from bad to worse. As the illustration shows, this slippery slope can drop off in two directions.

# Escape Responses

The three responses found on the left side of the slippery slope are commonly used by people who are more interested in avoiding or getting away from a conflict than resolving it.

Denial—One way to escape from a conflict is to pretend that no problem exists. Another way is to refuse to do what should be done to resolve a conflict properly. These responses bring only temporary relief and usually make matters worse (see 1 Sam. 2:22-25).

Flight—Another way to escape from a conflict is to run away. This may take the form of ending a friendship, quitting a job, filing for divorce, or leaving a church. Flight may be legitimate in extreme situations (see 1 Sam. 19:9-10), but in most cases it only postpones a proper solution to the problem (see Gen. 16:6-8).

Suicide—When people lose all hope of resolving a conflict, they may seek to escape the situation (or make a desperate cry for help) by attempting to take their own lives. Suicide is never a right way to deal with conflict (see Matt. 27:1-5).

# Attack Responses

The three responses found on the right side of the slippery slope are often used by people who are more interested in winning a conflict than in preserving a relationship.

Assault—Some people try to overcome an opponent by using various forms of force or intimidation, such as verbal attacks (including gossip and slander), physical violence, or efforts to damage a person financially or professionally (see Acts 6:8-15). Such conduct usually escalates conflict.

Litigation—Although some conflicts may legitimately be taken before a civil judge (see Acts 24:1-26:32; Rom. 13:1-5), lawsuits usually damage relationships, diminish our Christian witness, and often fail to achieve complete justice. This is why Christians are commanded to make every effort to settle their differences within the church rather than the civil courts (see Matt. 5:25-26; 1 Cor. 6:1-8).

Murder—In extreme cases, people may be so desperate to win a dispute that they will try to kill those who oppose them (see Acts 7:54-58). While most people would not actually kill someone, we should never forget that we stand guilty of murder in God's eyes when we harbor anger or contempt in our hearts toward others (see 1 John 3:15; Matt. 5:21-22).

# Conciliation Responses

The Gospel Is the Key to Peace. A true peacemaker is guided, motivated, and empowered by the gospel, the good news that God has forgiven all our sins and made peace with us through the death and resurrection of his Son (Col. 1:19-20). Through Christ he has also enabled us to break the habit of escaping from conflict or attacking others, and he has empowered us to become peacemakers who can promote genuine justice and reconciliation (Col. 3:12-14).

The six responses found on the top portion of the slippery slope are directed at finding a just and mutually agreeable solution to a conflict. These responses may be divided into two categories: personal peacemaking responses and assisted responses:

Personal peacemaking responses are carried out in private between the parties themselves. Although it is appropriate for one or both parties to seek advice on how to implement these responses, they should normally try to resolve their differences one-on-one before asking others to intervene in the dispute.

Overlook an offense—Many disputes are so insignificant that they should be resolved by quietly and deliberately overlooking an offense. "A man's wisdom gives him patience; it is to his glory to overlook an offense" (Prov. 19:11). Overlooking an offense is a form of forgiveness, and involves a deliberate decision not to talk about it, dwell on it, or let it grow into pent-up bitterness or anger.

Reconciliation—If an offense is too serious to overlook or has damaged our relationship, we need to resolve personal or relational issues through confession, loving correction, and forgiveness. "[If] your brother has something against you ... go and be reconciled" (Matt. 5:23-24). "Brothers, if someone is caught in a sin, you who are spiritual should restore him gently" (Gal. 6:1; see Matt. 18:15). "Forgive as the Lord forgave you" (Col. 3:13).

Negotiation—Even if we successfully resolve relational issues, we may still need to work through material issues related to money, property, or other rights. This should be done through a cooperative bargaining process in which you and the other person seek to reach a settlement that satisfies the legitimate needs of each side. "Each of you should look not only to your own interests, but also to the interests of others" (Phil. 2:4).

If the parties cannot resolve a dispute through personal peacemaking, they should pursue one of the assisted responses. This will require that they seek help from other people in their church or community.

Mediation—If two people cannot reach an agreement in private, they should ask one or more objective outside people to meet with them to help them communicate more effectively and explore possible solutions. "If he will not listen [to you], take one or two others along" (Matt. 18:16). These mediators may ask questions and give advice, but they have no authority to force you to accept a particular solution.

Arbitration—When you and an opponent cannot come to a voluntary agreement on a material issue, you may appoint one or more arbitrators to listen to your arguments and render a binding decision to settle the issue. "If you have disputes about such matters, appoint as judges even men of little account in the church" (1 Cor. 6:4).

Accountability—If a person who professes to be a Christian refuses to be reconciled and do what is right, Jesus commands his or her church leaders to formally intervene to hold him or her accountable to Scripture and to promote repentance, justice, and forgiveness: "If he refuses to listen [to others], tell it to the church" (Matt. 18:17).

As you can see, the escape responses only postpone a proper solution to a problem, and attack responses usually damage relationships and make conflicts worse. Therefore, you should generally try first to deal with conflict personally and privately by using one of the first three conciliation responses (overlooking, discussion, or negotiation). To learn how to carry out these steps in a biblically faithful manner, see the Biblical Principle material which follows.

# See Conflict as an Opportunity

Conflict is not necessarily bad or destructive. Even when conflict is caused by sin and causes a great deal of stress, God can use it for good (see Rom. 8:28-29). As the Apostle Paul wrote in 1 Corinthians 10:31-11:1, conflict actually provides three significant opportunities. By God's grace, you can use conflict to:

- Glorify God (by trusting, obeying, and imitating him)

- Serve other people (by helping to bear their burdens or by confronting them in love)

- Grow to be like Christ (by confessing sin and turning from attitudes that promote conflict).

These concepts are totally overlooked in most conflicts because people naturally focus on escaping from the situation or overcoming their opponent. Therefore, it is wise to periodically step back from a conflict and ask yourself whether you are doing all that you can to take advantage of these special opportunities.

# Glorify God

When the Apostle Paul urged the Corinthians to live "to the glory of God," he was not talking about one hour on Sunday morning. He wanted them to show God honor and bring him praise in day-to-day life, especially by the way that they resolved personal conflicts (see 1 Cor. 10:31).

As mentioned above, you can glorify God in the midst of conflict by trusting him, obeying him, and imitating him (see Prov. 3:4-6; John 14:15; Eph. 5:1). One of the best ways to keep these concerns uppermost in your mind is to regularly ask yourself this focusing question: "How can I please and honor the Lord in this situation?"

# Get the log out of your own eye

One of the most challenging principles of peacemaking is set forth in Matthew 7:5, where Jesus says, "You hypocrite, first take the plank out of your own eye, and then you will see clearly to remove the speck from your brother's eye."

There are generally two kinds of "logs" you need to look for when dealing with conflict. First, you need to ask whether you have had a critical, negative, or overly sensitive attitude that has led to unnecessary conflict. One of the best ways to do this is to spend some time meditating on Philippians 4:2-9, which describes the kind of attitude Christians should have even when they are involved in a conflict.

The second kind of log you must deal with is actual sinful words and actions. Because you are often blind to your own sins, you may need an honest friend or advisor who will help you to take an objective look at yourself and face up to your contribution to a conflict.

When you identify ways that you have wronged another person, it is important to admit your wrongs honestly and thoroughly. One way to do this is to use the "Seven A's of Confession:"

- Address everyone involved (Prov. 28:13; 1 John 1:8-9)

- Avoid if, but, and maybe (don't make excuses; Luke 15:11-24)

- Admit specifically (both attitudes and actions)

- Apologize (express sorrow for the way you affected someone)

- Accept the consequences (Luke 19:1-9)

- Alter your behavior (commit to changing harmful habits; Eph. 4:22-32)

- Ask for forgiveness

The most important aspect of getting the log out of your own eye is to go beyond the confession of wrong behavior and face up to the root cause of that behavior. The Bible teaches that conflict comes from the desires that battle in your heart (James 4:1-3; Matt. 15:18-19). Some of these desires are obviously sinful, such as wanting to conceal the truth, bend others to your will, or have revenge. In many situations, however, conflict is fueled by good desires that you have elevated to sinful demands, such as a craving to be understood, loved, respected, or vindicated.

Any time you become excessively preoccupied with something, even a good thing, and seek to find happiness, security or fulfillment in it rather than in God, you are guilty of idolatry. Idolatry inevitably leads to conflict with God ("You shall have no other gods before me"). It also causes conflict with other people. As James writes, when we want something but don't get it, we kill and covet, quarrel and fight (James 4:1-4).

There are three basic steps you can take to overcome the idolatry that fuels conflict. First, you should ask God to help you see where your have been guilty of wrong worship, that is, where you are focusing your love, attention, and energy on something other than God. Second, you should specifically identify and renounce each of the desires contributing to the conflict. Third, you should deliberately pursue right worship, that is, to fix your heart and mind on God and to seek joy, fulfillment, and satisfaction in him alone.

As God guides and empowers these efforts, you can find freedom from the idols that fuel conflict and be motivated to make choices that will please and honor Christ. This change in heart will usually speed a resolution to a present problem, and at the same time improve your ability to avoid similar conflicts in the future.

# Go and show your brother his fault

Another key principle of peacemaking involves an effort to help others understand how they have contributed to a conflict. Before you rush off to confront someone, however, remember that it is appropriate to overlook minor offenses (see Prov. 19:11). As a general rule, an offense should be overlooked if you can answer "no" to all of the following questions:

- Is the offense seriously dishonoring God?

- Has it permanently damaged a relationship?

- Is it seriously hurting other people? and

- Is it seriously hurting the offender himself?

If you answer "yes" to any of these questions, an offense is too serious to overlook, in which case God commands you to go and talk with the offender privately and lovingly about the situation (see Matt. 18:15). As you do so, remember to:

- Pray for humility and wisdom

- Plan your words carefully (think of how you would want to be confronted)

- Anticipate likely reactions and plan appropriate responses (rehearsals can be very helpful)

- Choose the right time and place (talk in person whenever possible)

- Assume the best about the other person until you have facts to prove otherwise (Prov. 11:27)

- Listen carefully (Prov. 18:13)

- Speak only to build others up (Eph. 4:29)

- Ask for feedback from the other person

- Recognize your limits (only God can change people; see Rom. 12:18; 2 Tim. 2:24-26)

If an initial confrontation does not resolve a conflict, do not give up. Review what was said and done, and look for ways to make a better approach during a follow up conversation. It may also be wise to ask a spiritually mature friend for advice on how to approach the other person more effectively. Then try again with even stronger prayer support.

If repeated, careful attempts at a private discussion are not fruitful, and if the matter is still too serious to overlook, you should ask one or two other people to meet with you and your opponent and help you to resolve your differences through mediation, arbitration, or church discipline (see Matt. 18:16-20; 1 Cor. 6:1-8; for more guidance on getting such help)

# Go and be reconciled

One of the most unique features of biblical peacemaking is the pursuit of genuine forgiveness and reconciliation. Even though Christians have experienced the greatest forgiveness in the world, we often fail to show that forgiveness to others. To cover up our disobedience we often use the shallow statement, "I forgive her—I just don't want to have anything to do with her again." Just think, however, how you would feel if God said to you, "I forgive you; I just don't want to have anything to do with you again"?

Praise God that he never says this! Instead, he forgives you totally and opens the way for genuine reconciliation. He calls you to forgive others in exactly the same way: "Bear with each other and forgive whatever grievances you may have against one another. Forgive as the Lord forgave you" (Col. 3:12-14; see also 1 Cor. 13:5; Psalm 103:12; Isa. 43:25). One way to imitate God's forgiveness is to make four specific promises when you forgive someone:

- I will not think about this incident.

- I will not bring this incident up and use it against you.

- I will not talk to others about this incident.

- I will not allow this incident to stand between us or hinder our personal relationship.

Remember that forgiveness is a spiritual process that you cannot fully accomplish on your own. Therefore, as you seek to forgive others, continually ask God for grace to enable you to imitate his wonderful forgiveness toward you.

# Negotiate in a Biblical Manner

Even when you manage to resolve personal offenses through confession and forgiveness, you may still need to deal with substantive issues, which may involve money, property, or the exercise of certain rights. These issues should not be swept under the carpet or automatically passed to a higher authority. Instead, they should be negotiated in a biblically faithful manner.

As a general rule, you should try to negotiate substantive issues in a cooperative manner rather than a competitive manner. In other words, instead of aggressively pursuing your own interests and letting others look out for themselves, you should deliberately look for solutions that are beneficial to everyone involved.

As the Apostle Paul put it, "Do nothing out of selfish ambition or vain conceit, but in humility consider others better than yourselves. Each of you should look not only to your own interests, but also to the interests of others" (Phil. 2:3-4; see Matt. 22:39; 1 Cor. 13:5; Matt. 7:12).

A biblical approach to negotiation may be summarized in five basic steps, which we refer to as the PAUSE Principle:

- Prepare (pray, get the facts, seek godly counsel, develop options)

- Affirm relationships (show genuine concern and respect for others)

- Understand interests (identify others' concerns, desires, needs, limitations, or fears)

- Search for creative solutions (prayerful brainstorming)

- Evaluate options objectively and reasonably (evaluate, don't argue)

If you have never used this approach to negotiation before, it will take time and practice (and sometimes advice from others) to become proficient at it. But it is well worth the effort, because learning the PAUSE principle will help you not only to resolve your present dispute but also to negotiate more effectively in all areas of your life.

# Be Prepared for Unreasonable People

Whenever you are responding to conflict, you need to realize that other people may harden their hearts and refuse to be reconciled to you. There are two ways you can prepare for this possibility.

First, remember that God does not measure success in terms of results but in terms of faithful obedience. He knows that you cannot force other people to act in a certain way. Therefore he will not hold you responsible for their actions or for the ultimate outcome of a conflict.

All God expects of you is to obey his revealed will as faithfully as possible (see Rom. 12:18). If you do that, no matter how the conflict turns out, you can walk away with a clear conscience before God, knowing that his appraisal is, "Well done, good and faithful servant."

Second, resolve that you will not give up on finding a biblical solution. If a dispute is not easily resolved, you may be tempted to say, "Well, I tried all the biblical principles I know, and they just didn't work. It looks like I'll have to handle this another way (meaning, 'the world's way')."

A Christian should never close the Bible. When you try to resolve a conflict but do not see the results you desire, you should seek God even more earnestly through prayer, the study of his Word, and the counsel of his church. As you do so, it is essential to keep your focus on Christ and all that he has already done for you (see Col. 3:1-4). It is also helpful to follow five principles for overcoming evil, which are described in Romans 12:14-21:

- Control your tongue ("Bless those who curse you;" see also Eph. 4:29)

- Seek godly advisors (identify with others and do not become isolated)

- Keep doing what is right (see 1 Pet. 2;12, 15; 3:15b-16)

- Recognize your limits (instead of retaliating, stay within proper biblical channels)

- Use the ultimate weapon: deliberate, focused love (see also John 3:16; Luke 6:27-31)

At the very least, these steps will protect you from being consumed by the acid of your own bitterness and resentment if others continue to oppose you. And in some cases, God may eventually use such actions to bring another person to repentance (see 1 Sam. 24:1-22).

Even if other people persist in doing wrong, you can continue to trust that God is in control and will deal with them in his time (see Psalms 10 and 37). This kind of patience in the face of suffering is commended by God (see 1 Pet. 2:19) and ultimately results in our good and His glory.

# Get Help from Above

None of us can make complete and lasting peace with others in our own strength. We must have help from God. But before we can receive that help, we need to be at peace with God himself.

The Peacemaker's Pledge

A Commitment to Biblical Conflict Resolution

As people reconciled to God by the death and resurrection of Jesus Christ, we believe that we are called to respond to conflict in a way that is remarkably different from the way the world deals with conflict.1 We also believe that conflict provides opportunities to glorify God, serve other people, and grow to be like Christ.2 Therefore, in response to God's love and in reliance on his grace, we commit ourselves to respond to conflict according to the following principles:

Glorify God — Instead of focusing on our own desires or dwelling on what others may do, we will rejoice in the Lord and bring Him praise by depending on His forgiveness, wisdom, power, and love, as we seek to faithfully obey his commands and maintain a loving, merciful, and forgiving attitude.3

Get the Log out of Your Own Eye — Instead of blaming others for a conflict or resisting correction, we will trust in God's mercy and take responsibility for our own contribution to conflicts—confessing our sins to those we have wronged, asking God to help us change any attitudes and habits that lead to conflict, and seeking to repair any harm we have caused.4

Gently Restore — Instead of pretending that conflict doesn't exist or talking about others behind their backs, we will overlook minor offenses or we will talk personally and graciously with those whose offenses seem too serious to overlook, seeking to restore them rather than condemn them. When a conflict with a Christian brother or sister cannot be resolved in private, we will ask others in the body of Christ to help us settle the matter in a biblical manner.5

Go and be reconciled — Instead of accepting premature compromise or allowing relationships to wither, we will actively pursue genuine peace and reconciliation—forgiving others as God, for Christ's sake, has forgiven us, and seeking just and mutually beneficial solutions to our differences.6

By God's grace, we will apply these principles as a matter of stewardship, realizing that conflict is an assignment, not an accident. We will remember that success in God's eyes is not a matter of specific results, but of faithful, dependent obedience. And we will pray that our service as peacemakers will bring praise to our Lord and lead others to know His infinite love.7

1 Matt. 5:9; Luke 6:27-36; Gal. 5:19-26.
2 Rom. 8:28-29; 1 Cor. 10:31-11:1; James 1:2-4.
3 Ps. 37:1-6; Mark 11:25; John 14:15; Rom. 12:17-21; 1 Cor. 10:31; Phil. 4:2-9; Col. 3:1-4; James 3:17-18; 4:1-3; 1 Peter 2:12.
4 Prov. 28:13; Matt. 7:3-5; Luke 19:8; Col. 3:5-14; 1 John 1:8-9.
5 Prov. 19:11; Matt. 18:15-20; 1 Cor. 6:1-8; Gal. 6:1-2; Eph. 4:29; 2 Tim. 2:24-26; James 5:9.
6 Matt. 5:23-24; 6:12; 7:12; Eph. 4:1-3, 32; Phil. 2:3-4.
7 Matt. 25:14-21; John 13:34-35; Rom. 12:18; 1 Peter 2:19; 4:19

Section Four - After the Trip

Follow Up Meetings

Each team leader should schedule a minimum of two follow up meetings after the trip has been completed.

### The first meeting should focus on debriefing the trip using the tools found in the debriefing section of the GO Team Manual and using the guidelines below.  Only participants of the trip should be allowed at the meeting.

2.  The second meeting should be a party/fellowship time.  Family and friends should be invited to share in stories, pictures, and a time of rejoicing.

Reporting to the church

- It is our desire to have your team give a report to the church.  Time constraints may restrict some of this activity.

- The Missions Office will coordinate dates for giving a report.

- We encourage a video report of no longer than four minutes to show in church.

- This report should be thought through before and during the trip.

- Team leadership should pursue sharing about their GO trip in as many Sunday congregations and communities of the church as possible.

Section Five - Miscellaneous Information

Global Mobilization Team Contact Information

Amy Richey (Chairman)

(616) 866-2566

Richard Damstra (Ukraine)

(616) 451-9410

Dave Thrasher (Kosovo)

(616) 243-65603

Scherlyn Vanhaitsma (Albania)

(616) 874-2367

Tom Ellsworth (Central Asia)

901-4166

YOU ARE RESPONSIBLE FOR YOUR TRAVEL ARRANGEMENTS, NOT THE MISSIONS OFFICE

TRAVEL CONNECTIONS

We’d encourage you to begin looking at your travel arrangements early.  Most travel providers provide good group rates if preparation is done well in advance.  You may use your own trusted travel agent or one of the following agencies that specialize in mission trips.  If you are using Calvary Church owned vehicles you must have turned in applications for pre-approval of drivers 60 days prior to your trip.  This information is available at the facilities office of the church.

The internet is a good resource as well to get initial prices.  It may not be helpful for group rates.  Some good sights include:

www.travelocity.com

www.orbitz.com

www.expedia.com

Recommended Agencies:

Raptim International Travel Inc.
North Fourth Street 145
Lewiston, NY 14092
U.S.A.
Tel +1 716 754 9232
Tel +1 800 777 9232
Fax +1 716 754 2881
Email: www.raptim.com
Office hours: Mon-Fri 08:30-18:00 hrs

Overseas Express Travel

2705 W. Howard Street
Chicago, IL 60645-1303
(773) 262-4971
(800) 343-4873
(773) 262-4406 (fax)

http://www.ovex.com/

MTS www.mtstravel.com

HARVEST INTERNATIONAL TRAVEL Phone  (972) 429-4689

A humorous way to introduce speaking with a translator is to use the translator’s skit.  Get another person in the group to help with this and then have the team evaluate what they say and heard.

# Translator’s Skit

Speaker						Translator (with an accent)

- Tell them I am pleased to be here.

- When you asked me at lunch to speak to you today, I had butterflies in my stomach.

- But now I’m really happy to have this opportunity to be with you.

- I’d like to talk with you today about contextualization of theology in the 3rd World setting.

- But first let me share with you my testimony.

- When I was a kid…

- I didn’t understand the implications of what Christ did for me when He died on the cross.

- But then He convicted me of it through His Holy Ghost.

- I had been a real lady-killer.  I loved a life of sex, booze, and drugs.

- He set me free.

- He made me a new creature

(Excited, faster and LOUDER)

- Now I have a new life. I’m forgiven my past.  I am part of the body of Christ.  They are all my family.  I’m so excited.  I want to tell you all about it.

- He says to tell you he’s very happy to be here.

- At lunch I ate some flies that got into my stomach before speaking today.

- It’s O.K.  I’m really happy to have a chance to eat them with you.

- I’d like to talk to you about a text from another world.

- First I want to share my ….????

- When I was just a small goat…

- I did not understand what happened when Christ died at the intersection.

- But a ghost arrested me for it.

- I had killed a lady.  Oh, I’m too embarrassed to translate what he just said.  But then he took medicine and got better.

- I was let go.

- I was made into a new animal.

- He’s very happy.  Please clap for him.

WORKING WITH YOUR ON-SITE MISSIONARIES

On-site missionaries can be a great asset when planning your church’s short-term mission.  Since they live in your destination country they will know the local language and culture.  They can assist you with information on issues such as security, visas, vaccinations, food availability, what to do for drinking water, local church “culture”, appropriate dress for team members, etc.

As a team leader or coordinator you need to be responsible for getting clear communication with your missionaries.  Many times missionaries who are not used to hosting teams and who have been on the field for a number of years have adjusted to doing things in the local manner, which is good.  But, maybe what they don’t realize is that for a team of 30 people, boiling drinking water just won’t work well.  You, the coordinator, need to discuss with the missionary well in advance just how it is that you will be able to obtain 45 gallons of drinking water a day for your team to survive in the hot and humid climate you’ll be working in.

My worst experience as a short term team leader centered around this very issue.  We had a large team and we were working in the desert on the north coast of Colombia.  It was the first year of a new summer missions program.  Our communication with the field was not the best.  The way we “solved” the drinking water shortage was by drinking soda all summer.  You may think that sounds great, but after awhile, Cornflakes and coke gets real old!  What compounded the problem was our lack of an onsite missionary advisor.  He lived several, through the desert, hours away.  He was onsite the first day for a few hours and didn’t make his appearance again till two weeks later, this time for about 45 minutes.  That was the last time we saw him for the whole summer. If someone was around who spoke English, we might have been able to figure out how to have fresh water.  Since we were right on the coast, even the “fresh” water  was tainted with salt.  The language barrier was another problem for us.  None of us spoke fluent Spanish.  The pastor we were working with was an Indian man who spoke his dialect and some Spanish.

If our communication with the on-site missionaries would have been clear, most of these problems could have been avoided.  The next year we took a team back to that same part of Colombia and worked with the same mission.  Believe me, it was a lot different!

Tell the on-site missionary what your goals are for the team.  What do you want the team to see and experience?  Are there particular types of work you want the team to see/be a part of?  A few years after our trips to Colombia we got to be on the other end of things as the on-site missionaries.  Because of our experience leading teams we were better able to host teams as they came to minister with us.  We had some teams that flew in on Friday night and wanted to work the whole time they were there.  They didn’t want to visit local churches on Sunday, they worked, building camp cabins for the missionary training institute we were establishing.  They didn’t go sight-seeing, they wanted to work.  We had other teams who had set agendas when they arrived and we as hosts adapted to their schedules.  Some wanted to be involved in construction 50% of the time and 50% of their time they wanted to be involved in outreach.  We would work this out months in advance because we as the hosts had to have ministry opportunities lined up with local pastors/churches or building materials on-site before the team would arrive.  Communication on the field is mostly slow and often hit or miss, so the on-site missionaries need to have plenty of time in advance to adequately prepare for your team’s arrival and ministry.

So, make sure your on-site missionaries know exactly what you are expecting of them.  For a team to be effective it is my observation that an on-site missionary needs to be assigned to a team pretty much full time.  What a great opportunity for the missionaries to pass on their vision!  One way we missionaries did this was to divide up the responsibility for the team.  Some worked with them on the construction project, someone else was assigned to head up the ministry opportunities, social and sight-seeing times, in country travel, etc.

Take time to think through as many of the details as possible and keep up a running dialog with your on-site missionaries, refining the details as you go.  Don’t be afraid to ask the nit-picky type questions.  Those little details are the ones that can make or break the success of your team.  After all, who would have thought that drinking water would have been a problem in the “tropical” country of Colombia.

TEAM LEADER FORMS

Team Proposal – General Information

Below is a list of items which must be present on the team proposal.  The Global Mobilization Team or the Missions Office is available to provide insight and help in thinking through these items if needed.

Purpose

What is the primary purpose of your trip?  What need will you be meeting on the mission field?

Goals

What are the goals for this trip?  In detail, how will you accomplish your primary purpose?

Dates

Provide the dates for the mission.  If possible, provide alternative dates as well.  What is the date on which the team must be selected?

Location

Where is this Global Outreach team going to minister?

Host Group

Who is inviting you, and/or hosting you at this location?

Participants

Who will be the participants in this mission?  Will the team be only open to certain people or groups (men, women, youth, etc.) or will it be open to all of Calvary Church or attendees from other churches?

Relationship to other Calvary Church ministries

Is there a connection with a ministry of Calvary Church?

Accountability

To whom is the team leader accountable throughout the logistical and spiritual journey of this mission trip?

Coordination with other Missionaries or Missions Groups

Is there a missionary or ministry other than Calvary Church that will be participating in this mission?  Has this missionary or ministry been informed of the details and plans of the trip?

Pre-trip Planning

What is the proposed method and schedule for preparing the individuals of the team for the mission and for building relationships among team members prior to the trip?

Debriefing and Reporting

How do you propose to debrief your team after the trip?  Mission trips can be profound in their effect on emotions and spiritual growth.  How do you propose to help your team members assimilate their experiences into their daily lives?  The team leader and one team member must provide the Global Mobilization Team with a short briefing on the success and effect of the mission trip, including final budget report.  Ideally this should take place within one month of returning.

Estimated Costs and Funding

Here an estimated budget must be submitted.  This must be provided before final approval can be given.

SAMPLE PROPOSAL

Calvary Church Global Outreach

TEAM PROPOSAL

PASTORAL STRENGTHENING AND CONGREGATIONAL OUTREACH TRIP TO INDIA

Overview

Five to six former pastors will travel to New Delhi to spend 10 days with Indian pastors as a pastoral strengthening/refreshing effort.  Each team member will live with an Indian pastor and his family.  The team will visit each pastor’s church twice during the stay to participate in worship and prayer as well as outreach to the congregation.

Purpose

This trip is primarily a “kingdom strengthening” trip.  The pastors who will be contacted do not have the resources available to most American pastors and also do not have the chance for weekend retreats.  The pastors on the team will do their best to provide a “retreat” environment for their Indian counterparts as well as hand carry to India multiple spiritual resources that will be a tremendous benefit to the ministry of the Indian pastors.  Also, team members will fellowship with each congregation and witness to them.

Goals

- To provide an international fellowship between the Indian and American pastors

- A mutual strengthening through sharing of testimonies, experiences, etc.

- To share customs and learn of the other person’s culture

- To strengthen the spiritual well being of the Indian pastors

- Provide a “retreat” environment for the Indian pastors as much as possible and to make every effort to ensure that they may receive blessings for a change

- Provide materials of spiritual encouragement and also provide instruction on their use

- Outreach to the congregation

- Meet with each congregation twice during the stay and share time in prayer as well as messages from the pulpit

- Witness to each congregation through personal testimony, experiences, etc.

- Provide leaders within the congregation with tools and knowledge of pastoral support

Dates

The trip is scheduled to leave on March 3, 2003 and return on March 14, 2003.  Alternatively, May 1 through May 12, 2003.

Team Leader

John Doe will serve as team leader.

Logistics Leader

Jane Doe will serve as the logistics leader.

Participants

Participation for this trip is limited to pastors.  While most participants will be retired pastors, those pastors who can get away without causing any neglect within their own church are more than welcome (encouraged) to come.

Relationship to other Calvary Church ministries

Calvary Church does not have an organizational contacts in the region of New Delhi that apply to this trip.  However, Jack Doe has served as missionary to New Delhi for the past five years and has been supported by Calvary Church.  It was through his eyes that the need for this trip was seen.

Accountability

Brian Johnson, team leader, and Jack Doe, logistics leader, have agreed to continually meet and pray with each other in the time leading up to this trip.  They have also agreed to keep each other on task.

Coordination with Missionary or Hosts

John Doe has been in continual contact throughout the planning process of this trip.  He was most responsible in selecting the dates as well as arranging accommodations and small details in India.

Training Plans

The team will be meeting no less than five times before departure.  Each pastor who is able to participate will be assigned to read Iron Sharpens Iron by Bill Smith.  This book is an excellent resource for teaching pastors to minister to other pastors.  The meetings will focus on the details of the trip and necessary preparations as well as a discussion of this book.

Debriefing and Reporting

Jon Doe, team leader, and Jane Doe, logistics leader, have designated themselves for the briefing to the Global Mobilization Team.  We also propose that after the trip we be given an opportunity to invite all members of Calvary Church to an open forum discussion some Sunday after the trip in which we may share experiences and answer questions.

Personal debriefing for the team will take place at Jon Doe’s house after the trip.  We will share personal experiences as well as discuss how we can apply what we learned to daily living.  This will occur within one month of returning.

Estimated Costs and Funding

Income

Registrations			600

Personal Funds		2200

Fund Raising			2000

STM Funds			1600

Total				6400

Expenses

Airfare				4800	6 @ 800

Car Rental			500

Gasoline			100

Training Expenses		100

Materials			450

Food				150

Misc. Expenses		300

Total Expenses		6400

All contributions received will be used for team expenses.  No refunds will be returned to participants.  Unused funds will be used at the discretion of the Missions Committee for future Global Outreach Trips.

Signature 							Date

##### Global Outreach Team Proposal

FORM #1

Purpose

Goals

Dates

Location

Host Group

Desired Participants

Relationship to other Calvary Church ministries

Accountability

Coordination with other Missionaries or Missions Groups

Pre-trip Planning

Debriefing and Reporting

Estimated Costs and Funding

Signed								Date

(Turn into Missions Office)

Team Leader Agreement

(One copy remains with Team Leader, one with Missions Office)

FORM #2

By the grace of God and in agreement with the responsibilities described I ,

Do agree to perform the duties of a Global Outreach Team Leader as presented in this document.  I will

    - Submit a project form to the Global Mobilization Team for Missions Committee and Deacon approval

    - Submit a detailed budget for the GO trip.

    - Attend Team Leader Training

    - Bring an apprentice Team Leader to the Team Leader Training.

    - Schedule a minimum of six meetings to prepare our Global Outreach Team.

    - Schedule on-sight meetings for our GO team.

    - Schedule follow-up meetings for our GO team.

    - Comply with the financial arrangements as outlined in this document.

    - Fulfill to the best of my ability the responsibility the Lord and Calvary Church has given me as a team leader.

Team Leader Signature							Date

Global Mobilization Chair Signature					Date

(Turn into Missions Office)

BUDGETING (possible categories)

FORM #3

Visas

Airfare

Train Fare

Bus Fare

Vehicle Rental

Fuel

Other Travel

Bibles/Books

Lodging

Meals

Rentals

Tools

Materials

Water

Printing

Postage

Crafts

Drama

Music

Promotion

T-Shirts

Travel Insurance

Excess Baggage

Tips

Gift to Missions Work

Retreat Expenses

Other

TOTAL				   TOTAL Per Person

| Calvary Church Project Form FORM #4 (*Projects will not be presented unless form is complete*) # Directions: Mission Projects need approval at the team level and then are routed to the Missions Committee. All other projects need standing committee approval and then are routed to the Finance Team or Deacons for final approval. Please be aware of the time that is involved in this process and that many committee meetings may take place once a month. Please be aware also, that we will not be able to process any funds received before proper approval has been given. The same deadlines for check requests and purchase orders apply to disbursement of project funds. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Title: |  | Initiated by: |  |  |  | Term (start & end date): |  |
| PROJECT TYPE: | - Ongoing Support - Retirement Support |  | - Sunday School Project Class Name______________________ |  |  |  | - Short Term Mission - Other_____________ |
| DESCRIPTION: Purpose: Dates: Number of Attendees Cost per Attendee Total Cost |  |  |  |  |  |  |  |
| Ministry Team Team Name______________________________________ - Approved Date________________________ - Not Approved Chairperson__________________ - Tabled (signature) |  |  |  |  |  |  |  |
| Missions Committee(if applicable) - Approved Date __________________________ - Not Approved Chairperson_____________________ - Tabled (signature) |  |  |  |  | Deacon or Finance Team Approval - Approved Date _______________________ - Not Approved Chairperson__________________ - Tabled (signature) |  |  |
| COMMENTS (future considerations, concerns, necessary follow-up, etc.): |  |  |  |  |  |  |  |
| Financial Services Account #: |  |  |  | Funds disbursed to: Name ___________________________________ Address _________________________________ City, State Zip ____________________________ |  |  |  |
| Staff Contact Person: |  |  |  |  |  |  |  |
| Class Contact Person: |  |  |  |  |  |  |  |
| Class Contact Phone: |  |  |  |  |  |  |  |

Turn into Missions Office

Global Outreach Team

FORM #5

# Advertisement Form

Trip Name:

Team Leader Name:

Team Leader Contact Information:

Home Phone

Work Phone

Email

Cell

Please place a star where there is any information above you would like to keep unpublished.

Dates of Trip:

Cost of Trip:

Ministry Information:  (what will you be doing?)

Any Limitations on who can attend? (ex: sex, age)

Informational Meeting

Date:

Time:

Location:

1 Copy for Team Leader Records

1 Copy to Missions Administrative Assistant.  Date turned in:			.

Please turn this form in by Wednesday, December 17, 2003.

SHORT TERM MISSIONS PHONE RECOMMENDATION FORM

Team Member Name:

FORM #6

Reference Name:

To the reference:  “We value your comments and request that you give a full and candid report, so that fair consideration may be given to the applicant.  Please be assured that all comments will be held in strictest confidence.”

How long have you known the applicant?

How well do you know the applicant?

Have you observed the applicants spiritual life?

How would you describe it?	Positive	Neutral		Negative

If possible, please explain your response.

Please evaluate the applicant in the following areas.  (1 being low, 10 high.)

Self Starter    	1	2	3	4	5	6	7	8	9	10

Cooperative		1	2	3	4	5	6	7	8	9	10

Leadership		1	2	3	4	5	6	7	8	9	10

Servant hood		1	2	3	4	5	6	7	8	9	10

Disciplined		1	2	3	4	5	6	7	8	9	10

Kindness		1	2	3	4	5	6	7	8	9	10

Loyalty		1	2	3	4	5	6	7	8	9	10

Reliability		1	2	3	4	5	6	7	8	9	10

Anything else we need to know about this person?

Recommended		Prefer not to make a recommendation	     Not recommended

Signature								Date of Reference

Team Leader

Name and phone # of another person who knows this person well.

If you were the team leader, would you have any reservations about taking this person on this trip?

Calvary Church GO Team Interview Form

FORM #7

Name of Applicant

GO Trip

Share with us in a few minutes about your spiritual journey.  From Salvation to where you are right now.

Why do you believe God would want you to attend this GO trip?

Share your insights about who you are in the following areas:

Self Starter:

Cooperative:

Leadership:

Servanthood:

Disciplined:

Kindness:

Loyalty:

Reliability:

Team Player:

What are your desires after you return from this trip?  How do you want to make an impact?

Interviewer:

Recommended		Prefer not to make a recommendation	Not recommended		  Signature										Date

Calvary Church

Statement of Doctrine

FORM #8

Section A.  The Holy Scriptures

We believe that “All Scripture is God-breathed,” by which we understand the whole of the book called the Bible.  We do not take this statement in the sense in which it is sometimes said that the works of human genius are inspired, but in the sense that the Holy Spirit gave the very words of the sacred writings to holy men of old.  His divine inspiration is not in different degrees, but extends equally and fully to all parts of these writings, historical, poetical, doctrinal, and prophetical, and to the smallest word and inflection of a word, provided such a word is found in the original manuscripts (Mk. 12:26, 36; Acts 1:16, 2:4; 1 Cor. 2:13; 2 Tim. 3:16-17; 2 Pet. 1:21).

Section B.  The Godhead

We believe that the Godhead eternally exists in three persons, the Father, the Son, and the Holy Spirit, and that these three are one God, having precisely the same nature, attributes, and perfections, and are worthy of the same homage, confidence, and obedience (Mt. 28:19-20; Mark 12:29; Jn. 1:1-4; Acts 5:3-4; 2 Cor. 13:14; Heb. 1:1-3; Rev. 1:4-6).

Section C.  The Father

We believe that God is a Spirit (Jn. 4:24), who is limitless (1 Ki. 8:27; Acts 17:28), eternal (Ps. 90:2), self-existent (Ex. 3:14), unchangeable (Mal. 3:6), omnipotent (Rev. 19:6), omniscient (Ps. 147;5), omnipresent (Ps. 139:7-11), holy (1 Pet. 1:15-16), righteous (Jn. 17:25), loving (1 Jn. 4:8), good (Ps 100:5), truthful (Dt. 32:4; Jn. 14:6), and sovereign (Eph. 1:11; Rom. 8:28-29).  We believe that God the Father, understood as the first person of the Trinity, orders and disposes all things according to His own sovereign purpose and grace (We believe that God the Father, understood as the first person of the Trinity, orders and disposes all things according to His own sovereign purpose and grace (Eph. 1:3-11; Rom. 8:28).  He has decreed for His own glory all things that come to pass (Isa. 43:7; 48:11; Eph. 1:11).  He is the Creator of all things (Gen. 1:1, 31; 1 Cor. 8:6; Eph. 3:9), and to Him is due all glory (Rom. 11:36).  In His sovereignty He is not the author of sin nor does He approve it (Hab. 1:13; Jas. 1:13); nor does He violate the accountability of moral, intelligent creatures (Jn. 3:16; Lk. 13:3; 1 Pet. 1:17).  The Father hood of God involves both His designation within the Trinity and His relationship with created mankind.  As Creator, He is Father to all men (Acts 17:29; Eph. 4:6), but He is spiritual Father only to believers (Rom. 8:14-15; 2 Cor. 6:18; Gal. 3:26; 4:6).  He saves from sin all those who come to Him; and He becomes, upon adoption, Father to His own (Jn. 1:12; Eph. 1:5; Heb. 12:5-9).

Section D.  The Person and Work of Christ

We believe in the virgin birth and the bodily resurrection of Jesus Christ.  We believe that the Scripture, from first to last, centers about our Lord Jesus Christ in His person and work, and in His first and second coming.  Therefore, no chapter, even of the Old Testament, is properly read or understood until it leads to Him.  Moreover, we believe that all the Scripture from first to last, including every chapter of the Old Testament, was designed for our practical instruction (Mt. 1:23; Lk. 24:27, 44; Jn. 5:39; Acts 17:2-3; 18:28; 26:22-23; 28:23; Rom. 15:4; 1 Cor. 10:11; 15:4).

Section E.  The Person and Work of the Holy Spirit

We believe that the Holy Spirit is not an influence but a divine person, the source and power of all acceptable worship and service.  He is our abiding Comforter and Helper who never departs from the Church nor from the weakest saint.  He is ever present to testify of Christ, seeking to occupy us with Him and not with ourselves nor with our experiences (Jn. 7:38-39; 14:16-17; 15:26; 16:13-14; Acts 1:8; Rom. 8:9; Phil. 3:3)

Section F.  The Creation and Fall of Man

We believe that man, originally created in the image and after the likeness of God, fell from his high and holy estate by eating the forbidden fruit.  As the consequence of his disobedience, the threatened penalty of death was then and there inflicted, so that his moral nature was not only grievously injured by the fall, but he totally lost all spiritual life, becoming dead in trespasses and sins and subject to the power of the devil (Gen. 1:26; 2:17; Jn. 5:40; 6:53; Eph. 2:1-3; 1 Tim. 5:6; 1 Jn. 3:8).

Section G.  The Total Depravity of Man

We believe that this death, or total corruption of human nature, has been transmitted to the entire race of man, the Man Christ Jesus alone excepted.  Hence, every child of Adam is born into the world with a nature that not only possesses no spark of divine life, but is essentially and unchangeably bad, being enmity against God and incapable by any educational process whatever of subjection to His law (Gen. 6:5; Ps. 14;1-3; 51:5; Jer. 17:9; Jn. 3:6; 5:12-19; 8:6-7).

Section H.  The Necessity of the New Birth

We believe that because of this universal depravity and death in sin, no one can enter the Kingdom of God unless born again, and that no degree of reformation, however great; no attainment in morality, however high; no culture, however attractive; no humanitarian and philanthropic schemes and societies, however useful; no baptism or other ordinance, however administered; can help the sinner to take even one step toward heaven.  Only a new nature imparted by the Holy Spirit through the Word is absolutely essential to salvation (Isa. 64:6; Jn. 3:5,18; Gal. 6:15; Phil. 3:4-9; Tit. 3:5; Jas. 1:18; 1 Pet. 1:23).

Section I.  Salvation Accomplished by Christ

We believe that our redemption has been accomplished solely by the blood of our Lord Jesus Christ.  He was made to be sin and a curse for us, dying for us.  We believe that no repentance, no feeling, no faith, no good resolution, no sincere efforts, no submission to the rules and regulations of any church, or of all the churches that have existed since the days of the apostles, can add in the very least to the value of that precious blood or to the merit of that finished work which was wrought for us by Christ, who united in His person true and proper divinity with perfect and sinless humanity (Lev. 17:11; Mt. 23:28; Rom. 5:6-9; 2 Cor. 5:21; Gal. 3:13; Eph. 1:7; 1 Pet. 1:18-19).

Section J.  Eternal Security

We believe that it is the privilege not only of some believers but of all who are born again by the Spirit through faith in Christ as revealed in the Scriptures to be assured of their salvation the very day they take Him to be their Savior.  This assurance is not founded on any fancied discovery of their own worthiness, but wholly on the testimony of God in His written Word, exciting within His children filial love, gratitude, and obedience 9Lk. 10:20; Jn. 6:47; Rom. 8:33-39; 2 Cor. 5:1, 6-8; 2Tim. 1:12; 1 Jn. 5:13).

Section K.  The Believer’s Standing

We believe that Christ, in the fullness of the blessing He has secured by His obedience unto death, is received by faith alone, and that the moment we trust in Him as our Savior we pass out of death into everlasting life, being justified from all things.  We are accepted before the Father according to the measure of His acceptance, loved as He is loved, having His place and portion, and linked with Him in spiritual oneness forever (Jn. 5:24; 17:23; Acts 13:39; Rom. 5:1; Eph. 4:6, 13; 1 Jn. 4:17; 1 Jn. 5:11-12).

Section L.  The Walk of the Believer

We believe that we are called with a holy calling to walk not after the flesh but after the Spirit, and so to live in the Spirit that we should not fulfill the lusts of the flesh.  The flesh, being the “old man” in fallen Adam, is still in us to the end of our earthly pilgrimage and needs to be kept constantly in subjection in the place of death (separation from control0 in Christ, or it will surely manifest its presence to the dishonor of His name (Rom. 8:12-13; 13:14; Gal. 5:16-25: Eph. 4:22-24; Col. 3:1-10; 1 Pet. 1:14-16; 1 Jn. 3:5-9).

Section M.  The Church

We believe that the Church is composed of all who are united by the Holy Spirit to the risen and ascended Son of God, that by the same Spirit we are all baptized into one body, whether we be Jews or Gentiles, and thus being members one of another, we are responsible to keep the unity of the Spirit in the bond of peace, rising above all sectarian prejudices and denominational bigotry, and loving one another with a pure heart fervently (Mt. 16:16-18; Acts 2:32-47; Rom. 12:5; 1 Cor. 12:12-27; Eph. 1:20-23; 4:3-10; Col. 3:14-15).

Section N.  The Church Ordinances

We believe that two ordinances or directives have been committed to the local church:  baptism and the Lord’s Supper (Acts 2:38-42).  Christian baptism by immersion (Acts 8:36-39) is symbolic of the beginning of the Christian life and is the holy and beautiful testimony of a believer affirming personal faith in the crucified, buried, resurrected, and ascended Savior.  This spiritual union with Christ in death to the old life in Adam and resurrection to a new life in Christ is illustrated by water baptism (Rom. 6:1-11; Gal. 2:20; Col. 2:11-12).  It is also a sign of identification with the Body of Christ, the Church (Acts 2:41-42).  The Lord Jesus has commanded His Church to “go and make disciples of all nations, baptizing them in the name of the Father and of the Son and of the Holy Spirit” (Mt. 28:19).  We believe that the Lord’s Supper is the ordinance or directive proclaiming the continual commemoration of the death of Christ until He comes, and should be always preceded by worshipful self-examination for sin (1 Cor. 11:23-32).  We also believe that even though the elements of communion are only symbolic of the flesh and blood of Christ, the Lord’s Supper is to be a blessed time of fellowship with the risen Christ.

Section O.  The Ministry and Spiritual Gifts

We believe that the Holy Spirit bestows spiritual gifts on all believers for Christian service and the edification o the Church.  These spiritual gifts are to be exercised according to biblical guidelines (Rom. 12:3-8; 1 Cor. 14:4-11; 1 Pet. 4:10-11).

We believe the church age was initiated through the ministry of the apostles and prophets, and was accompanied by sign-gifts* to confirm their message.  However, we do not practice, teach, encourage, or endorse sign-gifts for this present age (1 Cor. 12:28-31; 13:8-10: 14:1-28; 2 Cor. 12:12; Eph. 2:19-22; Heb. 2:3-4).  We believe that God hears and answers prayer in accordance with His own will for the healing of the sick and afflicted (Jn. 14:13-14; 15:7; 1 Jn. 5:14-15).

*Theses sign-gifts are apostleship, healing, speaking in tongues, interpretation of tongues, prophesying, words of knowledge, and miracles.

Section P.  The Eternal State

We believe that the souls of those who have trusted in the Lord Jesus Christ for salvation pass into His presence immediately at death, and there remain in conscious bliss until the resurrection of the body at His coming, when should and body reunited will be associated with Him forever in the glory.  The souls of unbelievers remain after death in conscious misery until the final judgment of the great white throne at the close of the  millennium, when soul and body reunited will be cast into the lake of fire, not to be annihilated, but to by punished with everlasting destruction from the presence of the Lord, and from the glory of His power (Lk. 16:19-26; 23:43; 2 Cor. 5:8; Phil. 1:23; 2 Thess. 1:7-9; Jude 6:7; Rev. 20:11-15).

Section Q.  Eschatology- The Doctrine of the Last Things

We believe that the world will not be converted during the present dispensation but is fast ripening for judgment, and there will be a fearful apostasy in the professing Christian body.  Therefore, the Lord Jesus will come in person to rapture the Church, followed by a tribulation period, followed by the millennial age, when Israel will be restored to their own land, and the earth will be full of the knowledge of the Lord.  This personal and premillennial advent is the blessed hope set before us in the Gospels, for which we should be constantly looking (Lk. 12:35-40; 17:26-30; 18:8; Acts 15:14-17; 2 Th. 2:3-8; 2 Tim. 3:1-5; Tit. 2:11-15).

Signed								Date

Team Assistants

FORM #9

Music Coordinator

Drama Coordinator

Team Medic

Media Coordinator

Luggage Coordinator

Carry-on Coordinator

Food Coordinator

Tool Coordinator

Other Ministry Coordinator

Language Coordinator

Logistics Leader

Spiritual Life Leader

| CASH ADVANCE RECONCILIATION FORM #10 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name |  |  |  |  | Date of Advance |  |  |  |
| Event |  |  |  |  | Amount of Advance |  | $ |  |
| Section 1 - US$ |  |  |  |  | Section 2 - Foreign Currency |  |  |  |
| Receipt # | Date | Description | US$ |  | Receipt # | Date | Description | Foreign $ |
|  |  | Total |  |  |  |  | Total |  |
|  |  | Total US $ from other side |  |  |  |  | Total Foreign from other side |  |
|  |  | Sub Total Section 1 |  |  |  |  | Sub Total Section 2 |  |
|  |  |  |  |  |  |  | Exchange Rate |  |
|  |  | Total from Section 2 - Foreign |  |  |  |  | Total Converted US $ |  |
|  |  | Total Receipts |  |  |  |  |  |  |
|  |  | US $ Returned |  |  |  | Date |  |  |
| Prepared By |  |  |  |  |  |  |  |  |
| Turn into Finance Office |  |  |  |  | Calvary Church Staff Supervisor |  |  |  |

Meeting Dates Form

FORM #11

Time/Date of Meetings					Location of Meeting

Please include all team meetings/Info meeting, debrief meeting, and any retreats.  You will need to set up the room for your meeting with Calvary Church’s Facilities office 956-9377 x217.

1 Copy for Team Records

1 Copy to Missions Department AA – Date turned in_____________

Copies for Informational Meeting – Be sure to include on that copy that all team meetings are mandatory!

Name:

calvary

church

missions

Address:

Home Phone

Work Phone

E-Mail

Birthday

GO Global Outreach

# Team

Member

Profile

Time at Calvary

Prayer Requests and Other Information:

calvary

church

missions

Name:

Address:

Home Phone

Work Phone

E-Mail

Birthday

GO Global Outreach

Team

Member

Profile

Time at Calvary

Prayer Requests and Other Information:

calvary

church

GLOBAL

OUTREACH

APPLICATION

CALVARY CHURCH

GLOBAL OUTREACH APPLICATION

Thank you for your interest in short term missions! To help us get to know you better, each adult applying needs to fill out a separate application.  Students applying for a Student Missions Trip must also fill out a separate application.

PERSONAL

Name:								Date:

Address:

Phone:						(H) 					(W)

Age:

Fax:					 Email:

Citizenship:

Passport #: 						Expires on:

If you have children traveling with you, please list information below:

Name						Gender			Date of Birth

____________________________________

CHURCH INFORMATION

Which church are you associated with?

Name:												____________

Address:																							________________________

Phone:						Member 		Since

Attendee 		 Since

Please briefly describe your church activities/involvement:

What GO trip are you applying for?

EDUCATION/TRAINING/EXPERIENCE

Please list any education or training that could be useful for this trip:

Please list any natural talents/gifts you are aware of:

Besides church, list any other extracurricular activities/hobbies you participate in:

(For applicants who have attended a previous short-term trip) Please describe how you have applied this training/experience in local ministry:

What is your goal for this trip? (Specifically, what new challenges are you hoping to overcome? In which areas are you expecting to grow?)

What languages other than English, if any, do you speak/write? Share your ability in each language.

# SPIRITUAL

Explain how you came to know Christ as your Savior and Lord. Attach a separate sheet if necessary.

If someone were interested in becoming a Christian, what would you say to him/her?

Please list 3 references of people who have known you at least one year. At least one should be a pastor/ministry leader.

Name				Relationship					Phone