Six Month Trip Timeline

Six Months

  - Choose Site / Missionary

  - Establish Purpose of Trip

  - Establish Goals / Skills Sets

  - Choose Team Leaders

  - Choose Dates

  - Approval by Mission Staff

Five Months

  - Advertise Trip

    - Bulletin

    - Branches

    - Mission Newsletter

    - Mid-Size Communities Staff

  - Recruit Team

  - Interview Team

  - Identify Hardship Cases

  - Establish Budget

  - Project Code

  - Apply for Passport / Visas

Four – Three Months

  - Schedule Pre-Trip Meeting

  - Build Team

  - Division of Responsibilities

  - Prayer / Donor Support Letter (4 months)

  - Make Appoint at Health Clinic to Start Immunization

  - Collect Materials for Trip

  - Set Up Travel Arrangements

  - Cultural / Missionary Preparation

Two Months

  - Plan Debriefing / Attend Workshop

  - Delegate Responsibilities

  - Final Payments Due

  - Work Out Trip Logistics  (see handout)

  - Donations / Prayer Support

  - Team Leader Organizes Emergency Contact List, Etc.

One Month

  - Personal Packing

  - Review of Trip

  - Donations / Prayer Support

  - Submit Necessary Information to GO Team Folder

On-Site

  - Daily Schedule

  - On-going Communication with Missionary

  - Daily De-Briefing

  - Team Leader Accountability

  - Evaluation of Team and Site for Future Global Outreach Teams

Post-Trip

  - Evaluation

  - De-Briefing

  - Prayer / Donor Support Presentations

  - Mid-Size Community Presentations

Source: Christ Church of Oak Brook, Oak Brook, IL.  Doug Calhoun, missions pastor.  Used with permission.