Phases and Time-Line of a Mission Trip

Guidelines for team leaders

- Initial planning (Summer)

  - Work out with the church partner the purposes of the trip, and thus the age group(s), number of Bible Church team members, and general activities. Also work out the dates.

  - Identify the team leader and co-leader.

  - Announce the trip in the church, with the means depending on the intended team (Families? Young adults? Musicians?)

  - Select the team using a written form if the team needs to be limited in number or particular qualifications.

- Team and trip preparation (Winter-Spring)

  - Assign readings

  - Set a schedule of preparation meetings and what needs to be communicated at each.(I suggest no fewer than six meetings. Potlucks that rotate between the homes of the members contribute to team building)

  - Hold the meetings

  - Identify prayer supporters for each member; give list of email addresses to the Mission administrative assistant.

  - Make reservations (flights, guesthouse, safari)

  - Share plans with the host(s); modify in need be

  - Commissioning service on a Sunday morning

- The trip (Summer)

  - Lead the team through the activities (of course)

  - Hold regular devotions and debriefing meetings with the team

  - Keep track of expenditures and any receipts

  - Keep a record of names and contact information for anyone we may want to contact again.

  - Send regular (every other day?) email communications to the church to distribute to prayer partners.

  - Meet with partnership leaders to debrief about this trip and talk about the next one

  - Scout out potential new activities for the next trip

- Re-entry (Summer)

  - Return church equipment/supplies to Megan

  - Have each person respond in writing to assigned reflection questions

  - Final team debriefing meeting

  - Meet one-on-one with any team member as needed

  - Prepare and deliver reports to congregation

    - Sunday morning

    - Monday evening mission dinner

    - Separate event for prayer supporters (optional)

    - Articles for the Fold and website

  - Turn in accounting and receipts to the church

  - Resolve any lingering payments

- Follow-up (From return until next trip departure)

  - Immediate written thanks to hosts and prayer supporters

  - Immediately complete short trip report form and hand in to the Pastor of Mission.

  - Print and file any partnership leader trip journal; also distribute to leaders of other partnerships. Hand in to Megan and Jim.

  - Meet with the Pastor of Mission to debrief, either as a co-leader or report on the trip if he wasn’t part of it.

  - Receive and review the team’s written responses to the reflection questions. Identify potential improvements for the next trip and inform the Pastor of Mission.

  - Identify with team members what they will do to spread the lessons from the trip throughout the congregation. Help them accomplish these things where need be (e.g., arrange for them to talk with a particular group?) and check with them periodically to see if they have done what they aimed to do.

Source: Chapel Hill Bible Church, Chapel Hill, North Carolina.  Used by permission of Jim Thomas.

For a trip taking place the following summer.