Team Preparation Schedule

MEXICO 2005

Sept	 13    INFORMATIONAL MEETING

Applications available

Oct 	    4     Applications due

11     TEAM TRAINING #1   7:00pm  in the Conference room

Team Building and raising support

Meet your team, strengthen teamwork concepts and take team photo

Information for writing your support letter and creating your supporter list

Nov	   8      TEAM TRAINING #2   7:00pm

Cross Cultural Ministry

Receive team brochure to mail with your support letter.

Mail letters and brochure out this week.

Dec	  13    	TEAM TRAINING #3   7:00pm

Presenting the Gospel Message, Your testimony

Work project/Children’s ministry and Surgical team strategy time

Personal contribution of $100.00 due

Jan       10	TEAM TRAINING #4   7:00pm

Ministry Planning, Packing, Travel documents, Health

Plan for travel immunizations with Kent County Health Dept.    336-3096

Make prayer calendar.

Bring copy of either your passport or original birth certificate

17	Deadline for funds to be from supporters.

Feb 	   7	TEAM TRAINING #5   7:00pm

Ministry Planning Continued

- Packing of team supplies

27     	 Team commissioning on Sunday

Mar	 4-13	Mission trip to Mexico

20	Team reporting and presentation in church

???		Team reunion

Source: Sunshine Community Church, Grand Rapids, MI.  Beth Hutchings, Short Term Team Leader.  Used with permission.