Trip Preparation Timeline

Country of: 	_________________________________

Tentative dates: _________________________________

Team leader:	_________________________________

Dear Team Leader,

This checklist is designed as a tool to help you plan, organize, recruit and then lead your team on a successful mission trip overseas. Because College Church STAMP teams work in various language and culture groups, work at a variety of ministries, work in various world climates, and occur at different times of the year, no single checklist will fit each team100%.

As you use this tool, please communicate to the missions pastor any items you feel should have been added to this document or perhaps deleted as not needed.

Hopefully this check list will get you to the field.  It is not intended to be checklist for on-field activities.

20 MONTHS

	Committee sends STAMP team proposal request forms to College Church missionaries 	and national seminaries with whom we partner. These forms are normally sent in 	September.

18 MONTHS

	If necessary, a reminder is sent to each missionary and national seminary.

	Returned forms are reviewed by the STAMP committee. STAMP committee works with 	the missionary or national seminary to strengthen the proposal and resolve any unanswered questions.

16 MONTHS

	Returned forms are evaluated by the STAMP committee. Projects selected by the 	STAMP committee are submitted to the BOM for approval.

	BOM approves STAMP Project proposals

	Formal dates are set for the trip.

	Size of team is determined

	The STAMP committee and missions pastor discuss team leader possibilities and create 	a list of team leader candidates.

15 - 13 MONTHS

	Team leader candidates are contacted until a qualified team leader is found.

	The STAMP committee submits a team leader candidate to the pastoral staff and BOM 	for approval.

	The pastoral staff and BOM approve the recommended leader.

	Team leader sets up accounting procedures

12 MONTHS

	Team leader is oriented to STAMP philosophy, purpose, and goals by the missions 	pastor or STAMP chairperson.  Team leader receives copy of STAMP policy and team 	leaders’ handbook.

	Team leader is introduced to team liaison from the STAMP committee. The role of the 	STAMP liaison is explained.

	Team leader contacts College Church sponsoring missionary to begin gathering 	information necessary to create an appropriate team.

	A tentative (ball park) budget is set which takes into consideration the following items.

  Air fare

  Ground transportation (taxis, bus, train, vehicle rental, waterways)

  Lodging

  Meals

  Visa fees

  Insurance

  Taxes (airport, entry/exit, vehicle tolls)

  Required supplies (construction, VBS, literature, equipment etc)

 Host/hostess gift

 Immunizations

  Recreation in host country (personal expense not reflected in total)

	Verify current visa requirements

	Determine starting date to begin visa applications if needed. DATE IS _______________

	Begin compiling a reading list for the team

11 MONTHS (this process may take 2-3 months)

	Team leader communicates with on field missionary to formulate mutual expectations.

	Team leader makes a presentation to the congregation detailing the basics of the project 	and creating congregational awareness and ownership of the STAMP team.

- Promote in adult communities.

- Promote on the web.

- Promote on Sunday & Wednesday nights.

- Promote in the Fellowship and in the Front Line News.

- Coordinate with missions education committee about putting information on the missions table.

- Promote in the children’s program.

	Team leader, with help from the STAMP committee, recruits his or her team.

	Team leader purchases copies of the Short Term Mission Preparation Guide, Before You Pack Your Bag Prepare Your Heart by Cindy Judge. Copies can be ordered by calling 	630-682-3122. An order form can be downloaded from www.campfireresources.com and 	faxed to 630-682-0926. Since the missions department at College Church may have copies of this book on hand, be sure to check with the administrative assistant for missions before ordering copies directly from Campfire Resources.

     	Team member candidates submit their applications to the STAMP Committee. The STAMP Committee screens and interviews all applicants and submits a list of recommended candidates to the Board of Missions for approval.

	Each candidate is approved by BOM.

	Team leader communicates with STAMP committee liaison concerning the preparation 	progress of the team.

8 MONTHS

FOCUS - Expectations

	STAMP team leader leads first meeting with team members already approved to join the 	team. The team may not be complete yet, but the nucleus of the team should be in place.

- The team reviews the purpose and goals of STAMP. These goals can be summarized as Service, Exposure, Discipleship, and Recruitment.

- The team is oriented to their STAMP team project including some information about their host missionaries.

- The team is oriented to this timeline and to the FAQ document included in the STAMP handbook.

- Team members write to their host missionary and request that they receive their host’s missionary newsletter and/ or regular e-mail update.

- The team leader provides a suggested reading list that pertains to the host culture, geography, history, economy.

- The team leader distributes the following release forms to the team: STAMP Medical agreement and Parent/Guardian Acknowledgment Release and Consent form (for participants under age 18).

- The team leader verifies that all team members have, or will have, international healthcare coverage. Most team members will need to obtain HealthCare Abroad or HealthCare Global international travel insurance from Wallach & Company (www.wallach.com). (HealthCare Global international travel insurance is a cheaper option for teams overseas longer than two weeks). Wallach will send each participant a Certificate of Insurance and Medex pamphlet.

- Team members who do not have a passport that will be valid for at least six months beyond the last day of the STAMP trip, must apply for a new passport. Passport applications can be obtained from the Post Office in downtown Wheaton.

- As a team, discuss chapters 1 & 2 (“Whatever it takes!” and “What’s in this for you? What’s in this for them?”) from the “Before You Pack Your Bag Prepare Your Heart” short term mission preparation guide.

    	Final team member candidates are recruited by the team leader and team members. 	These candidates submit their applications to the STAMP Committee. The STAMP 	Committee screens and interviews all applicants and submits a list of recommended 	candidates to the Board of Missions for approval.

	Each candidate is approved by BOM.

	At least six prayer partners per team member recruited

	A means of keeping the project before the congregation is developed (posters, displays, 	prayer cards, powerpoint presentation).

7 MONTHS

FOCUS - team building and fund raising

	Team meeting & prayer. The team should be complete by this time.

- Assignment of individual roles based on project activities (treasurer, nurse, head builder etc.)

- Each person discuss how his or her skills/gifts will contribute to the project

- Team building exercises.

- Look at what the Bible says about teamwork and relationships. Review the “one another” passages in scripture.

- Discussion of security issues

- what to say and not to say

- what to do or not do in the event of a crisis

   Discussion  and clarification of the release forms

- Optional:  Visit an agency (such as World Relief or International Students Inc) that can put the team in contact with nationals currently living near Wheaton who are from the country which will be visited.

- As a team, discuss Chapter 10 from PREPARE YOUR HEART “Being a Team Player.”

	Start gathering materials to be used on the project.

- VBS sessions

- Building materials

- Evangelistic talks

	Fund raising begins.

- A support letter template is created that can be used by all team members.

- Mailing lists are coordinated to ensure that no congregational member receives more than one request for support per project.

	Team leader communicates with STAMP committee liaison concerning the preparation 	progress of the team.

6 MONTHS

FOCUS – Spiritual Preparation

	Team meeting & prayer

- When you go on a STAMP team you are part of fulfilling a 4000 year old promise that through Abraham all the families on earth shall be blessed. Gen 12:3. One of the core goals of this trip is for you to grow in Christian character and your love for God.

- What are you doing now (before you go) to prepare yourself spiritually? What areas do you feel vulnerable? What parts of your spiritual armor do you need to put in place? Eph 6: 10 – 18

- What is your plan while you are on the trip to stay close to God? Is there a devotional guide you can go through as a team? A book of the Bible?

- What is your plan after you return? Before you go, schedule an individual and a team time for reflection and evaluation. Set aside time to process with the Lord and hear from him. Do this now!

- Each team member write their personal testimony and write a brief synopsis of the Gospel. Each of these explanations should be about 3 minutes long – not much longer. During the upcoming team meetings have each team member share their testimony.

- As a team discuss Chapter 6 from  PREPARE YOUR HEART “Learn their story; tell yours”

	Review Fund raising progress. Team members are encouraged to refer to the FAQ 	document in the STAMP handbook to answer their questions concerning the logistics of 	fundraising.

	STAMP Medical agreement and Parent/Guardian Acknowledgment Release and Consent 	form (for participants under age 18).completed, photocopies and 	submitted to Missions 	pastor. The team leader keeps a photocopy of each form.

	Each participant’s Certificate of Insurance and Medex pamphlet from Wallach is 	photocopied and submitted to Missions Pastor. The team leader keeps a photocopy of 	each form.

5 MONTHS

FOCUS - living conditions of team in host country

	Team meeting & prayer

- With the information currently available, describe the expected living conditions for the team while overseas

- Discuss housing, food, on site transportation, tentative work schedule (this will certainly change, however it always good to have a general idea.)

- Review expectations of host missionary, team leader, team members, national group to be served.

- One or two team members share their testimony.

- Progress reviews

- As a team discuss Chapter 4 from PREPARE YOUR HEART “Traveling outside your comfort zone.”

	Airfare locked in and reservations made.

	Photos

  passport

  promotion – take a team photo and individual photos of each team member.

  photos for church office (publicity or contingency)

  photos to leave with national friends

	Travel Documents (passport & visa) are obtained, updated, or in process.

	Immunizations administered. Hepatitis A, Typhoid, and Tetanus are common 	immunizations needed for many trips. Other medical requirements considered.  Get an 	update on malaria risk, or SARS or other highly contagious diseases possible in your 	area of 	service.

	Team leader communicates with STAMP committee liaison concerning the preparation 	progress of the team.

	Determine political stability of host country for security reasons

	Verify with missionary how funds will be obtained while on the field.

Travel with cash? Travelers Checks? ATMs? (In many countries, US currency must be in 	near mint condition to be accepted by foreign banks and currency exchange businesses. 	Don’t bring creased, taped or old bills. This is important!  GET NEW BILLS.)

4 MONTHS

Focus – cultural sensitivity

	Team meeting & prayer

- Review expectations of all parties concerned.

- Discuss cultural issues including dress, language, body language, music, literature, host country’s view of boy-girl relationships, US mannerisms that may or may not be appropriate in the team’s host culture. The dress code in most countries can be summarized as “Nice, casual clothes that are modest.”

- From the reading that people have been doing about their host culture, identify some aspects of the host culture that are particularly interesting, beautiful, noteworthy, or unique. Develop a sense of respect for the host culture and interest in the people of that country. If possible, invite someone from the host country (a national or a furloughing missionary) to talk about the culture.

- One or two team members share their testimony.

- Progress review

- As a team discuss Chapter 5 from PREPARE YOUR HEART “Are you an American first or a Christian first?”

	Notify missionary’s mission agency about upcoming trip

	Care for any agency paperwork that may be required

	Instruction on financial record keeping in the homeland prior to trip

	On field missionary notifies sponsoring mission board of pending trip

	Verify with missionary that on field housing has been procured

	Pay for airline tickets (or find out last date to pay)

	Optional:  Go to an ethnic restaurant representative of your host country

3 MONTHS

	Team meeting & prayer

- One or two team members share their testimony.

- As a team discuss Chapter 3 – PREPARE YOUR HEART “’How’ is more important than ‘what’.”

         Discuss follow-up options for team members after they return from this trip. Emphasize 	that this trip is part of an ongoing participation in the missions initiatives of College 	Church. Distribute the Next Steps document to each team member.

	Arrange a date with the Missions Administrative Assistant for the team to present their 	STAMP trip to the church at an evening service or Wednesday night prayer meeting.  Arrange a date for the team to be commissioned in an evening service.

         Health travel tips (see appendix)

	Review support raising

	Confirm all of team’s travel documentation is in hand or in process

	Confirm all of team’s immunizations are done or in process

	Confirm all of team’s overseas health insurance is in hand

	Confirm with on field missionary the tentative schedule.

	Team leader communicates with missionary to go over expectations

	Team leader communicates with STAMP committee liaison concerning the preparation progress of the team.

	Airline tickets in hand

2 MONTHS

	Team meeting & prayer

- If at all possible arrange a conference call with missionary

- Begin focus on training, rehearsals

- Team party to celebrate victories to date

- Discussion of dress code factors to be taken into consideration

- One or two team members share their testimony.

- As a team discuss Chapter 7 from PREPARE YOUR HEART “So what are so afraid of?”

	Verify political stability in host country for security reasons

	If applicable to the project, advance money to the sponsoring missionary for the pre-positioning of any supplies.

	Consult with on site missionary and determine how much cash, or travelers checks should carried

6 WEEKS

	Team meeting & prayer

As a team discuss Chapter 8 from PREPARE YOUR HEART “What is better, a vacuum cleaner or a broom?”

	Go over suggested packing list

	Discussion of luggage (suitcases versus duffle bags)

	Maximum permissible carry on bag – see appendix

	Maximum baggage total – see appendix

	Suggestions for making your luggage easily identifiable

	Carry on to have all indispensable items (one set clothes, toiletries, medicines)

	Recording expenses while overseas (See multi currency expense report in appendix.)

4 WEEKS

FOCUS - logistics

	Team meeting & prayer

As a team discuss Chapter 9 from PREPARE YOUR HEART “Top ten ways to be a good guest”

	Each team member has adequate wardrobe. Remember that the dress code in most 	countries can be summarized as “Nice, casual clothes that are modest.”

	Prescription medications adequate for trip. Team leader should receive a list from each 	team member of all prescription medications that each team member is taking!

	Emergency notification information for each person on hand, in church office,

and with mission agency.

 passport numbers

 current photo

 medical information

 mission agency contact person and phone number  #___________________

	Photocopies of the following documents for each team member are submitted to the 	Missions Pastor:

- complete identification information from passport, (inside cover and first page)

- plane ticket

- travel itinerary

	Team leader communicates with STAMP committee liaison concerning the preparation 	progress of the team.

	Confirm that everyone is prepared for his or her role on the team

	By this time all funds needed for the trip should be received.

3 WEEKS

	Team meeting & prayer

- As a team discuss CHAPTER 11 from PREPARE YOUR HEART “What if a Teammate drives you crazy.”

	All travel documents in hand

     	Stateside family knows how to get in touch with STAMP team members in case of 	emergency.

	Review NEXT STEPS document again and remind the team to be looking for ways that 	they can continue their missions involvement after the trip is over.

2 WEEKS

	Team meeting & prayer

- As a team discuss Chapter 12 from PREPARE YOUR HEART “Track what happens on your trip.”

	Written itinerary given to US family

	Arrange travel to airport

	Arrange pick up at airport upon return

1  WEEK

	On the Sunday evening prior to departure, congregational commissioning service and 	prayer.

	Team leader remind pastoral staff of the dates of their trip and request prayer for the 	team on those Sunday mornings that the team will be overseas. Hopefully, the team can 	be prayed for during the congregational prayer in the Sunday morning service.

	Reconfirm flights with international air carrier

	Verify political stability of host country for security reasons

	Pack indispensable items plus one change of clothes in carry on bag.

	Cash on hand for all anticipated cash expenses during travel

DAY BEFORE

	Contact all team members to ensure documentation is in hand

	Verify that no team member is carrying documents or anything else that will be 	challenged by authorities in a limited access country.

DAY OF DEPARTURE

	If feasible, gather at church prior to departure for prayer with pastoral staff, family 	members and supporters.

	Arrive at airport with sufficient time to handle security delays

	Team leader brings copies of the STAMP evaluation form to distribute to team members 	on the plane ride home from their host country.

	Team leader brings photocopies of the following documents for each team member:

- complete identification information from passport, (inside cover and first page)

- plane ticket

- travel itinerary

- Wallach travel insurance card

- Medical Release Form

- Parent/Guardian Acknowledgment Release and Consent form (for participants under age 18)

- List of prescription medicines

AFTER THE TRIP: FOLLOW-UP

	Team leader collects each team member’s post-trip evaluation. Preferably, these 	evaluations are completed on the plane trip home from the host country.

	Team leader develops a composite project evaluation based upon each team member’s evaluation and submits this composite evaluation to the STAMP committee within two months of the team’s return.

	The team gathers for at least one team debrief. During this time the STAMP committee liaison and Missions Pastor will present options for further missions involvement to the team. The team will also review the NEXT STEPS document.

	The team prepares a report for their donors. This report is often presented during a dessert or light supper for their donors. However, the team is free to choose whatever venue they prefer.

	The team also reports to the church during a Wednesday night prayer meeting or a Sunday evening service. The team leader should coordinate reporting arrangements with 	the Missions Administrative Assistant.

	Team leader submits a written financial report to the STAMP committee showing STAMP project expenditures and recommending how any remaining contributions (residual funds) are to be distributed. This is due one month within one month after completion of the STAMP project.

	One member of the team rotates on to the STAMP committee.

	The name of every STAMP participant is added to the missions mailing list to receive updates concerning future GO! meetings.

	The STAMP team leader meets with the Missions Pastor and, if possible, also with the STAMP committee for a final debrief of the trip.

	In October, STAMP participants are invited to attend the STAMP Ignition event to reunite with their teammates and explain their experience to STAMP applicants considering a STAMP trip the following year.

STAMP Team Trip Preparation Countdown

Source:  College Church, Wheaton, IL.  Bruce Wilson, Associate Pastor of Missions. April 25, 2005

Used with permission.